## Sheet1
RAG Status
On Track
Action Needed
Off Track
Extension Required
Timeline TBA
Hold
Completed
Key
Raised
Workgroup
Report Due to Panel
Code Admin Consultation
DFMR
FMR
Modification | June | July | August | September | October | November | RAG Status
GC0127 | [6 empty] | Workgroup meetings 2 and 3 July. Workgroup consultation to be issued mid July at earliest; therefore unlikely to meet August date. Seek Panel views on special Panel in September for GC0127/GC0128 or delay August Panel.
EU Code Emergency & Restoration: System Defence Plan
Workgroup
GC0128 | [6 empty] | Workgroup meetings 2 and 3 July. Workgroup consultation to be issued mid July at earliest; therefore unlikely to meet August date. Seek Panel views on special Panel in September for GC0127/GC0128 or delay August Panel.
EU Code Emergency & Restoration: System Restoration Plan
Workgroup
GC0125 | [6 empty] | Workgroup consultation to be issued 21 June (closing 12 July). Meeting 18 July to discuss responses.; workgroup vote to be arranged for w/c 5 August 2019 On track to meet Panel timetable.
EU Code Emergency & Restoration: Blackstart Testing
Workgroup
GC0123 | [6 empty] | Panel to note revised timeline - CAC to be issued 28 June, DFMR to Panel for Determination vote in August 2019, Appeal window 30 July - 20 August. Implement 3 September 2019
Clarifying references to NGET and Relevant Transmission Licensees
Workgroup
GC109 | [6 empty] | Panel to note that there is a risk to Panel agreed timetable (workgroup report to August Panel) - delay to issue of workgroup consultation due to volume of comments
Publication of System Warnings
Workgroup
GC 103 | [6 empty] | Agreed at Panel 30 May 2019 for timeline to be agreed at next workgroup meeting (date to be agreed)
Introduction of Harmonised Applicable Electrical Standards
Workgroup
GC107/113 | [6 empty] | Agreed at Panel 30 May 2019 for timeline to be agreed at 19 June workgroup meeting
Publication of generic and/ user specific values
Workgroup
GC117 | [6 empty] | Agreed at Panel 30 May 2019 for timeline to be agreed at next workgroup meeting (Panel to note that this was 10 July 2019 but will be September now due to prioritisation and resource availability)
Transparency for PGM Requirements
Workgroup
GC105 | [6 empty] | Panel to note that we will not meet August date as this is on hold due to quoracy issues and resource constraints. Timeline to be agreed at next workgroup meeting (date to be agreed).
System Incident Reporting
Workgroup
GC126 | [6 empty] | Agreed at Panel 30 May to continue to seek workgroup members. Panel to note that no further workgroup members so still not quorate.
Implementing Profiled Stable Import and Export Limits
Not Quorate