## Sheet1
RAG Status
On Track
Action Needed
Off Track
Extension Required
Timeline TBA
Hold
Completed
Key
Raised
Workgroup
Report Due to Panel
Code Admin Consultation
DFMR
FMR
Modification | June | July | August | September | October | November | RAG Status
GC0127 | [6 empty] | Furrther workgroup meetings held 2 and 3 July. Workgroup consultation to be issued mid July ; therefore unlikely to meet August date. Special Panel to be set up in September for GC0127/GC0128 as contingency.
EU Code Emergency & Restoration: System Defence Plan
Workgroup
GC0128 | [6 empty] | Furrther workgroup meetings held 2 and 3 July. Workgroup consultation to be issued mid July ; therefore unlikely to meet August date. Special Panel to be set up in September for GC0127/GC0128 as contingency.
EU Code Emergency & Restoration: System Restoration Plan
Workgroup
GC0125 | [6 empty] | Workgroup consultation issued 21 June (closing 12 July). Meeting 18 July to discuss responses.; workgroup vote to be arranged for w/c 5 August 2019 On track to meet Panel timetable.
EU Code Emergency & Restoration: Blackstart Testing
Workgroup
GC0123 | [6 empty] | CAC issued 28 June and closes 19 July, DFMR to Panel for Determination vote in August 2019, Appeal window 30 July - 20 August. Implement 3 September 2019
Clarifying references to NGET and Relevant Transmission Licensees
Workgroup
GC109 | [6 empty] | Panel to note that there is a risk to Panel agreed timetable (workgroup report to August Panel) - delay to issue of workgroup consultation due to volume of comments
Publication of System Warnings
Workgroup
GC 103 | [6 empty] | Agreed at Panel 30 May 2019 for timeline to be agreed at next workgroup meeting (date to be agreed)
Introduction of Harmonised Applicable Electrical Standards
Workgroup
GC107/113 | [6 empty] | Agreed at Panel 30 May 2019 for timeline to be agreed at 19 June workgroup meeting (now 10 July 2019)
Publication of generic and/ user specific values
Workgroup
GC117 | [6 empty] | Agreed at Panel 30 May 2019 for timeline to be agreed at next workgroup meeting (Panel to note that this was 10 July 2019 but will be September now due to prioritisation and resource availability)
Transparency for PGM Requirements
Workgroup
GC105 | [6 empty] | Panel to note that we will not meet August date as this is on hold due to quoracy issues and resource constraints. Timeline to be agreed at next workgroup meeting (date to be agreed).
System Incident Reporting
Workgroup
GC126 | [6 empty] | Agreed at Panel 30 May to continue to seek workgroup members. Panel to note that no further workgroup members so still not quorate.
Implementing Profiled Stable Import and Export Limits
Not Quorate