## Introduction
System Requirements Form (SRF) for NOA Stability Pathfinder Phase 2
ESO requirements have been published in the Expression of Interest (EOI) pack for Phase 2.
TOs must submit or confirm their solutions by returning completed SRF Part B by 17:00 8th Jan 2021.
In order to be considered in the economic assessment, TOs must submit completed SRF Parts C & E as part of the tender stage. Exact dates will be confirmed by ESO, the process timeline in the EOI pack provides indicative dates.
What can change?
The data submitted in this form must be to the best of your knowledge at the time of submission.
We acknowledge that some data may change as you progress through your design and through NOA stability pathfinder phase 2 process.
The following technical parameters will not be allowed to change post SRF submission deadline (in line with commercial solutions' EOI submission):
MVA rating
MW export/import
Connection location
Technology type
Fault/ SCL Infeed
MVAr Capability
The following technical parameters will be used in the assessment and need to be re-proven at the Technical Feasibility Stage. These can be change until the close of the feasibility stage. After this point no change will be allowed:
Inertia
Notes:
The Feasibility study will assess the performance of the solution against several clauses of the technical specification. Changes to the design post feasibility study that change the performance whilst still being compliant will be allowed but an updated feasibility report must be submitted.

## Part B - Option Detail
Part B: TO Proposed Option
| Response format | Response
Lead engineer | Provide a contact
TO Ref number | Enter a reference number if available
Option Name | Enter a option name if available
What is the proposed technology type? | e.g. synchronous/ grid forming converter/ other (if other please describe)
Does the proposed project meet the full technical specification? Are there any limitations with regards to meeting the technical requirements? | State yes/no. Provide additional information of any limitations and mitigations.
Can the proposed solution provide short circuit current response as defined in the technical specification? | State yes/no.
What is the expected instantaneous short circuit current contribution in rms at 100 ms after a 3-phase symmetrical fault? | State n/a if not known at this stage. This will need to be finalised during the technical feasibility stage for inclusion in the commercial tender submission.
Can the proposed solution provide an instantaneous inertia response as defined in the technical specification? | State yes/no
What is the expected inertia contribution in MJ? (as defined in the technical specification) | State n/a if not known at this stage. This will need to be finalised during the technical feasibility stage for inclusion in the economic assessment.
What is the rating of the proposed solution? (MVA) | Please state the rating in MVA. If solution comprises of multiple units, please state the rating of each unit.
Can the solution provide POD capability as stated in the technical specification? | State yes/no.
What is your steady state MVar absorption and injection range? | State the range.
What is your expected power consumption during normal operation (MW)? | State MW.
Is there anything else you would like to tell us about this technology? | Free text
Can you meet 90% availability criteria for Short Circuit Level? | State yes/no. If stating no, provide additional information on why you can not meet this criteria.
How do you expect to meet 90% availability for Short Circuit Level? | State technology/connections limitations
What is the your expected inertia availability and how do you propose to meet it? | State % availability over a year and any technology expectations/limitations. This will need to be finalised ahead of economic assessment.
Please provide the electrical substation location, stating the point on the transmission system that the solution is directly or radially connected to. | Substation name and voltage level
Are substation locations contained within V3 of SCL effectiveness list? | state yes/no
Are you able to include a single line diagram in this SRF submission? | State yes/no. If yes, please attach a single line diagram.
Can you meet the latest start date of 1st April 2024? | State yes/no and provide additional details as relevant. This latest start date will be reviewed following the connection review phase.
Are there any third-party dependencies to meeting this start date? | State any dependence to meet the start date that are outside of your direct control. E.g. planning/ funding/supply chain/ etc.
Enabling works:
Enabling works' requirement nature:
Are there any interactions between this option and other submitted options? For example mutually exclusive constraints. | State any other options that this option is exclusive with, prerequisites, etc.

## Part C - Outage Requirements
Part C: Outage Requirements (Required at the tender stage) | [7 empty] | Part C: Outage Requirements (Required at the tender stage)
TO Option Reference Number | EISD | Year of Outage | Circuits Out | Outage Duration (weeks) | Restrictions in Sequence of Works | Lead Engineer | Additional Comments | TO Option Reference Number | EISD | Year of Outage | Circuits Out | Outage Duration (weeks) | Restrictions in Sequence of Works | Lead Engineer | Additional Comments
TO Reference number. Must be same as Part B. | EISD | Year | Circuits Out | weeks | State whether the works must be done in a certain order | TO contact name in case of queries | If required, additional comments for ESO PSE | TO Reference number. Must be same as Part B. | EISD | Year | Circuits Out | weeks | State whether the works must be done in a certain order | TO contact name in case of queries | If required, additional comments for ESO PSE
|  | Year | Circuits Out | weeks | [5 empty] | Year | Circuits Out | weeks
|  | Year | Circuits Out | weeks | [5 empty] | Year | Circuits Out | weeks

## Part E -- Cost
Part E: Option's Costs (Required at the tender stage)
TO Reference Number | TO Reference number. Must be same as Part B.
WACC Used | % value used for Weighted Average Cost of Capital
Option Breakdown of Costs
Total Cost of New Assets/Works | Cost in £m | The total cost of completely new transmission assets or complete replacement of transmission assets.
Total Cost of New Assets/Works which are also separable | Cost in £m | The portion of the above cost where the ownership between these assets and other (existing) assets can be clearly delineated.
Total Cost of other Assets/Works | Cost in £m | The remaining cost of any assets/works which are not completely new transmission assets or complete replacement of transmission assets.
Total Cost of Consents | Cost in £m | Total cost of consents for this option
Total cost of Maintenance | Cost in £m | Total cost for maintaining the option during the Stability Ph2 assessment period (up to 2030)
Total Cost of Option | Cost in £m | Total cost of option (This should be the sum of 'New Assets/Works', 'other assets/works' and 'consents'
Annual Breakdown Spend to date column in the last year if possible and inflation adjusted for the current year. Please state the year this is costed in Use the columns marked * for mid-life refurbishment costs.
| Spend to Date | 2020/21 | 2021/22 | 2022/23 | 2023/24 | 2024/25 | 2025/26 | 2026/27 | 2027/28 | 2028/29 | 2029/30 | 2030/31 | 2031/32 | 2032/33 | 2033/34 | 2034/35 | 2035/36 | * | * | Total Cost of Option
Total spend for each year | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m | Cost in £m

## Part F - Publication Info
Part F: Publication information (Required at later stage of process)
TO Option Reference Number | Option publication name | Publication Description | Additional Comments
TO Reference number for option if available. Must be same as Part B. | The name of the option to be used in the NOA Stability Pathfinder Phase 2 outcome | The description of this option to be used in the publication | ESO will request consent from the TOs to publish the same level of information (including costs) consistent with the way information from a commercial option would be published when the tender process concludes.