## ALL ROLES
Role | Sub activity | Deliverable reference number | Deliverable name | Milestone Description | Milestone date | Milestone Status | Milestone completion date (quarter) | Deliverable commentary
1 | Ongoing activities | D1.1.1 | Balance Great Britain’s (GB) demand for energy with supply from generators around the clock | Meeting agreed metrics on balancing costs and security of supply. | Q4 2024-25 | Continuous activity |  | In Progress
1 | Ongoing activities | D1.1.2 | Maintain security of supply in real time and the ability to restart the system in the event of a partial or total loss of power | Meeting agreed metrics on balancing costs and security of supply. Carry out necessary work to meet GB restoration standard as described in A3.2. | Q4 2024-25 | Continuous activity |  | In Progress
1 | Ongoing activities | D1.1.3 | Maintain the integrity of the transmission network, while managing the economical operation of the system | Meeting agreed metrics on balancing costs and security of supply. | Q4 2024-25 | Continuous activity |  | In Progress
1 | Ongoing activities | D1.1.4 | Support development of new methodology under Trade and Cooperation Agreement and support European cooperation including and with the European Network of Transmission System Operators for Electricity (ENTSO-E) based on the outcome of Memorandum of Understanding (MoU) with ENTSO and CORESO based on the agreement with EU NRAs. Strategic relationships with European institutions are covered in Activity A21 Role in Europe. | Enhanced cooperation between EU and GB on electricity operation following EU-Exit. Support the development, delivery and implementation of new interconnector capacity calculation methodology. Maintain the delivery of the Day Ahead NG Security Analysis process in the NG control centre in preparation for future developments | Q4 2023-24 | Continuous activity |  | The Day Ahead Security Analysis process is being maintained in preparation for conclusion of ongoing capacity calculation methodology workstream. The capacity calculation methodology workstream is ongoing and NGESO has a preferred position but is still waiting for the EC to allow EU TSOs to engage with UK TSOs on this issue
1 | Ongoing activities | D1.1.4 | Support development of new methodology under Trade and Cooperation Agreement and support European cooperation including and with the European Network of Transmission System Operators for Electricity (ENTSO-E) based on the outcome of Memorandum of Understanding (MoU) with ENTSO and CORESO based on the agreement with EU NRAs. Strategic relationships with European institutions are covered in Activity A21 Role in Europe. | Enhanced cooperation between EU and GB on electricity operation following EU-Exit. Support the development, delivery and implementation of new interconnector capacity calculation methodology. Maintain the delivery of the Day Ahead NG Security Analysis process in the NG control centre in preparation for future developments | Q4 2024-25 | Continuous activity |  | The Day Ahead Security Analysis process is being maintained in preparation for conclusion of ongoing capacity calculation methodology workstream. The capacity calculation methodology workstream is ongoing and NGESO has a preferred position but is still waiting for the EC to allow EU TSOs to engage with UK TSOs on this issue
1 | Ongoing activities | D1.1.5 | Upgraded legacy balancing and situational awareness tools to deliver continued service levels whilst new tools are being developed | Priority asset health improvements made to meet expectations as per the ESO Roles Guidance. Priority Control Centre user enhancements made to tools, including greater automation and upgrades to the bulk dispatch tool, to help meet efficient balancing expectations in the ESO Roles Guidance and improved stability situational awareness such as oscillation monitoring. Increased PMU location coverage and improved situational awareness. Replacement FATE system fully integrated with legacy balancing tools. | Q4 2023-24 | Continuous activity |  | Dispatch Systems: •Complete: June 23 (BM Release 3) includes Situational awareness improvements to enable improved utilisation of bi-directional units and performance fixes around bulk instruction/bulk send of reason codes to BMUs. •Complete: July 23 (ASDP Release 14a) Ancillary Service Reform (ASR) Response enhancements allowing the Control Room to visualise Physical Notification data for dynamic contracted units. •Complete: September 23 (ASDP Release 15) Technical go live of the Regional Development Platform (RDP) MW Dispatch service on the ASDP. •Complete: September 23 (BM Interim Release 4) enables continued support, upgrades and security patches. This release also includes changes to inertia data integration to support the decommissioning of EBS. •Complete: Nov/Dec 23 (BM Release 4) includes improving unit and constraint visibility, streamline navigation across screens, remove nuisance alarms, and automate processes. Interfaces between BM and the Open Balancing Platform, changes to dispatch to enable the Balancing Reserve service, and migrated processes from EBS to BM to support decommissioning of EBS. •Complete: Dec 23 (ASDP Release 16) features of RDP MW Dispatch for UK Power Network (UKPN), Asset Health requirements and Control Room improvements to reduce risk and improve some existing functionality. •Future: Feb/Mar 24 (BM Release IR5) includes BM Performance improvement code optimisation and hardware upgrade Network Control (Situational Awareness): •Work continuing within the NCMS project to deliver oscillation monitoring within the new situational awareness tools. Access to improved offline analysis tooling has been provided early. •A new Oscillation situational awareness tool Proof of Concept has been delivered providing indication of Scottish Oscillations. •Connection to SSE production PMU data will be made in January 2024, enabling additional data to be available to ESO. •Replacement FATE system SAT tested and on schedule for delivery by end of Q4 FY24
1 | Ongoing activities | D1.1.5 | Upgraded legacy balancing and situational awareness tools to deliver continued service levels whilst new tools are being developed | Priority asset health improvements made to meet expectations as per the ESO Roles Guidance. Priority Control Centre user enhancements made to tools, including greater automation and upgrades to the bulk dispatch tool, to help meet efficient balancing expectations in the ESO Roles Guidance and improved stability situational awareness such as oscillation monitoring. Increased PMU location coverage including potentially within DNOs. | Q4 2024-25 | Continuous activity |  | Existing Systems: Continual Release in 2024/25 (FY25). Increased PMU location coverage and improved situational awareness (Network Control) - SSE production PMU data will be connected to ESO in January 2024, NGET PMU data not expected until Q4 FY25
1 | Ongoing activities | D1.1.6 | Assessment of future operability challenges communicated through the Operability Strategy Report. Published annually | Publish Operability Strategy Report | Q3 2023-24 | Complete | Q3 2023-24 | The report was published on the 28 Dec 2023. External comms followed w/c 8 Jan 2024. A webinar is scheduled for 23 Jan 2024.
1 | Ongoing activities | D1.1.6 | Assessment of future operability challenges communicated through the Operability Strategy Report. Published annually | Publish Operability Strategy Report | Q3 2024-25 | On track |  | Our annual process for producing and publishing the OSR begins in Q2 24-25.
1 | Ongoing activities | D1.1.7 | Produce and publish detailed forecasts and analysis, for both demand and generation, published at day ahead and other timescales. Forecasts will be enhanced using detailed statistical and machine learning approaches Provide data and insight to inform control centre decision making and performance review and integrate relevant IT projects into business as usual. | Solar Power Product Implementation | Q1 2023-24 | Delayed - Internal Reasons |  | The initial phase of the Solar Power product has been successfully developed in BP1, delivering value to consumers. In BP2, our objective is to transition the existing product from the current cloud solution to a strategic cloud solution and complete the remaining feature delivery To ensure alignment with consumer value and business requirements, we have re-prioritized the forecasting roadmap/backlog through the cost monitoring framework (CMF). While we continue to deliver consumer value , We are also doing revalidation of our current forecasting roadmap due to complexities associated with building new forecasting capability within a changing energy landscape, emerging data/technology and requirements/availability to improve forecasting models resulting in emerging new scope which will impact the roadmap
1 | Ongoing activities | D1.1.7 | Produce and publish detailed forecasts and analysis, for both demand and generation, published at day ahead and other timescales. Forecasts will be enhanced using detailed statistical and machine learning approaches Provide data and insight to inform control centre decision making and performance review and integrate relevant IT projects into business as usual. | Wind Power & National Demand Product Implementation | Q4 2023-24 | Delayed - Internal Reasons |  | In order to enhance deliverability confidence for the milestones and address an error in the BP2 submission (two milestones as one), a reassessment has been conducted regarding the priority, size, and complexity of this milestone. As a result, the milestone has been split into two separate milestones. The target completion dates have been set as follows: 1. Wind Power Milestone: Q1-FY25 2. National Demand Milestone: Q4-FY25 Change requests, duly approved, have been processed through the cost monitoring framework (CMF) to ensure regulatory compliance. The ongoing work on the Wind Power product recovery is progressing, and we anticipate the completion of its initial phase (MVP) by Q1-FY25 on the strategic cloud platform & phase 2 (Integration) subsequently Furthermore, the initial phase of the National Demand product has been successfully delivered during BP1, already providing value to consumers. Our objective is to transition this product from the current cloud solution to a strategic cloud solution and finalize the delivery of remaining features by March 25 in BP2. We are also undergoing a deliverability review of our forecasting roadmap (remainder of BP2/3). This due to complexities associated with building new forecasting capability within a changing energy landscape. This coupled with the emerging data/technology and requirements/availability to enable improved forecasting models is resulting in new/additional scope.
1 | Ongoing activities | D1.1.7 | Produce and publish detailed forecasts and analysis, for both demand and generation, published at day ahead and other timescales. Forecasts will be enhanced using detailed statistical and machine learning approaches Provide data and insight to inform control centre decision making and performance review and integrate relevant IT projects into business as usual. | Integration with OBP and DAP (as far as possible) | Q4 2024-25 | On track |  | Discovery Work is in progress for Integration Open Balancing platform (OBP) PEF/DAP Integration has been temporarily paused to re-validate needs and benefits in line with overall ESO Data strategy
1 | Ongoing activities | D1.1.8 | Trading solutions to deliver a safe, secure and economical strategy for the Control Centre | Delivery of a business continuity solution for trade capture and notification will allow trading to continue in the event that our primary systems became unavailable. Success looks like processes which are more robust and reliable, supported appropriately and automation is increased, reducing the risk of error occurring in manual processes. | Q4 2023-24 | Continuous activity |  | Trading tool (Faradyn) now in place which reduces trade data entry errors. Common failure point (LIMS) being investigated for improvements with trade notifications.
1 | Ongoing activities | D1.1.8 | Trading solutions to deliver a safe, secure and economical strategy for the Control Centre | Delivery of a business continuity solution for trade capture and notification will allow trading to continue in the event that our primary systems became unavailable. Success looks like processes which are more robust and reliable, supported appropriately and automation is increased, reducing the risk of error occurring in manual processes. | Q4 2024-25 | Continuous activity |  | Trading tool (Faradyn) now in place which reduces trade data entry errors. Common failure point (LIMS) being investigated for improvements with trade notifications.
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | We will have completed Programme Increment 8. Issued an end of Increment report on Earned Value and Progress. | Q1 2023-24 | Complete | Q1 2023-24 | Completed on 18 July as per original plan
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | We will have completed Programme Increment 9. The Increment is planned to deliver release 1, which will provide: Bi-directional Interfacing with BM and Base Energy Balacing Capabilities, including Market Data Processing, Margin Analysis, Meter Data Handling, Network Modelling, Demand Forecasting and crucially Bulk Optimisation and Dispatch. This will remove existing ineffficiencies in dispatch caused by having multiple systems and workarounds. | Q2 2023-24 | Delayed - Internal Reasons |  | Release 1 has been delivered aligned with revised plan agreed with industry, with the small BM unit and battery zones now live - the battery zone being additionally implemented based on industry feedback. Other activities have been prioritised in our revised plan with industry focusing on the important areas which add value. The remaining items in this milestone are delayed due to a technicality as a result of data misalignment between BP2 Annex 1 (Figure 1 - transformational deliverables roadmap), DD&T Annex 4 (Table 49 - Outcome Roadmap) and the Delivery schedule. We are delivering on schedule to the DD&T Annex 4 roadmap and as reported in the cost monitoring framework.
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | We will have completed Programme Increment 10. Issued an end of Increment report on Earned Value and Progress. | Q3 2023-24 | Delayed - Internal Reasons |  | Programme Increment 10 is currently in progress and was not originally planned for completion in Q3 2023-24, it was always planned for completion in Q4 2023-24 and is on track for completion against the original plan
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | We will have completed Programme Increment 11. The Increment is planned to deliver release 2, which will provide: Pre-Qualification & Contract Integration; improved Market Situational Awareness; Improved Demand and Network Situational Awareness; and Realtime Constraint Management. | Q4 2023-24 | Delayed - Internal Reasons |  | The delay is a technicality due to a data misalignment between BP2 Annex 1 (Figure 1 - transformational deliverables roadmap), DD&T Annex 4 (Table 49 - Outcome Roadmap) and the Delivery schedule. Programme Increments are not direclty related to OBP Releases. We are delivering on schedule to the DD&T Annex 4 roadmap and as reported in the cost monitoring framework. This states that Release 2 deliverable is due in Q3 FY25 not Q4 FY24 and is on track for Q3 FY25. This is also aligned with our communications via the quarterly balancing programme external engagement events. Programme Increment 11 delivers capabilities required to achieve release 2 completion in Q3 FY25.
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | We will have completed Programme Increment 12. Issued an end of Increment report on Earned Value and Progress. | Q1 2024-25 | On track |  | On track as per plan
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | The Balancing Transformation will have completed Programme Increment 13. The Increment is planned to deliver release 3, which will provide: Unit regstration integration; Predicted generation through PEF integration; Mastery of Network contraints; and the first release of the National Optimiser. | Q2 2024-25 | Delayed - Internal Reasons |  | The delay is a technicality due to a data misalignment between BP2 Annex 1 (Figure 1 - transformational deliverables roadmap), DD&T Annex 4 (Table 49 - Outcome Roadmap) and the Delivery schedule. Programme Increments are not direclty related to OBP Releases. We are delivering on schedule to the DD&T Annex 4 roadmap and as reported in the cost monitoring framework. This states that Release 3 deliverable is due in Q1 FY26 not Q2 FY25 and is on track for Q1 FY26. This is also aligned with our communications via the quarterly balancing programme external engagement events. Programme Increment 13 delivers capabilities required to achieve release 3 completion in Q1 FY26.
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | We will have completed Programme Increment 14. Issued an end of Increment report on Earned Value and Progress. | Q3 2024-25 | On track |  | On track as per plan
1 | Enhanced Balancing Capability | D1.2.1 | (Now known as 'Future of Balancing') Enhanced balancing tool built and developed in a modular fashion that will incorporate machine learning and artificial intelligence. It will enable us to schedule and dispatch a greater number of market participants than today | We will have completed Programme Increment 15. The Increment is planned to deliver release 4, which will provide: Frequency Data integration; replacement of User written response requirements; Inertia Monitoring; and Frequency Response Management. | Q4 2024-25 | Delayed - Internal Reasons |  | The delay is a technicality due to a data misalignment between BP2 Annex 1 (Figure 1 - transformational deliverables roadmap), DD&T Annex 4 (Table 49 - Outcome Roadmap) and the Delivery schedule. Programme Increments are not direclty related to OBP Releases. We are delivering on schedule to the DD&T Annex 4 roadmap and as reported in the cost monitoring framework. This states that Release 4 deliverable is due in Q3 FY26 not Q4 FY25 and is on track for Q3 FY26. This is also aligned with our communications via the quarterly balancing programme external engagement events. Programme Increment 15 delivers capabilities required to achieve release 4 completion in Q3 FY26.
1 | Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Requirements Reports | Integrate inertia data with Data and Analytics Platform | Q2 2023-24 | Complete | Q3 2023-24 | Improvements to the DAP platform ingesting inertia data have been made enabling enhanced displays to be created as additional operational data is integrated into DAP. This milestone should have aligned with that shown in Annex 4 (DDT) of BP2 which is March 2024 and has delivered the improved integration ahead of this date. Continued enhancements will be made to dashboards to increase benefits to operational users.
1 | Enhanced Balancing Capability | D1.2.2 | Develop inertia monitoring capabilities and other tools to address emerging technology and system management issues (as required), as outlined in future Operability Requirements Reports | Integrate tools created with network control tool Inertia monitoring tools integrated with DAP and enhanced balancing capability | Q4 2024-25 | On track |  | These integrations are likely to be via DAP and final delivery will align with the end project (OBP and Network Control / User console) priorities and timelines.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Look Ahead Iteration 1 / VSAT/OSA hosted in new DCs | Q1 2024-25 | On track |  | Sample Input Look Ahead data has been developed, work is ongoing with vendor to map this data for use in the Look Ahead toolset
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Look Ahead functionality running in Development Environments | Q2 2023-24 | Delayed - Internal Reasons |  | Dates to be revised to align with new Data Centre delivery dates. Not expected to knock-on to any other milestones
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Commence Build of Voltage Stability Analysis Tool (VSAT) and Online Stability Assessment (OSA) Tool Environments | Q3 2023-24 | Complete | Q3 2023-24 | Complete - awaiting Data Centre delivery.
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Shadow Control Centre established Initial Data and Analytics Platform (DAP) integration | Q4 2023-24 | On track |  | Shadow Control facilities to be developed as part of the training suite for new NCMS with the option to develop further into a proposed FSO Contingency Control Centre post-project completion. DAP integration target date remains March 2024
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | NGET receiving RTU Data DAP & balancing integration | Q2 2024-25 | On track |  | DAP integration target date remains March 2024 Balancing integration target date remains September 2024
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Serial RTU connections removed | Q3 2024-25 | On track |  | RTU PoC in progress with third parties, expected outcome Jan 24 - this milestone delivery will be dependent on both ESO and NGET progress with their respective SCADA replacement deliveries
1 | Transform Network Control | D1.3.1 | Develop and deliver new real-time situational awareness tool, so Control Centre engineers can better understand changing network limitations, leading to a more efficient risk-based operation of the system | Deliver integrated network control tool (inc VSAT & Look Ahead OSA), including its specific digital twin | Q4 2024-25 | Delayed - Internal Reasons |  | Date to be changed to October 25 following a rebase line of plan that has taken place to understand the impact of GE product pivot to new GridOS technology.
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Common Information Model (CIM) Integration Requirements Complete | Q3 2023-24 | Complete | Q2 2023-24 | CIM model integration requirements completed and aligned with NCMS product delivery plan
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Integrate with enhanced balancing tool | Q4 2023-24 | Delayed - Internal Reasons |  | Reviewed against latest NCMS and Balancing delivery plans and integration target date is now September 2024. No anticipated knock-on to other milestones. Delay is caused by a few internal factors: - - NCMS Pivot to GridOS - the focus on the pivot to GridOS from an NCMS perspective has meant the integration work with OBP (enhanced balancing tool) has been re-prioritised. - Due to the complexity of both the NCMS and OBP toolsets, requirement development for the interfaces and functionality to be shared between the two tools has taken longer than expected and is still ongoing in a number of areas (for example Constraint Visualisation). A high level plan for delivery of the integrations between NCMS and OBP are now in place.
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Common Information Model (CIM) Integration Complete | Q3 2024-25 | On track |  | CIM model integration aligned with NCMS product delivery plan
1 | Transform Network Control | D1.3.2 | Enhanced network modelling capabilities with online analysis of voltage and power flow profiles closer to real time | Integrate with Network Control Management System (NCMS) | Q4 2024-25 | On track |  | integration aligned with NCMS product delivery plan
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Complete UI/UX requirements for ENCC Operator Console | Q1 2023-24 | Complete | Q1 2023-24 | User requirements completed and design is now underway.
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Commence Design Phase | Q2 2023-24 | Complete | Q2 2023-24 | User requirements completed and conceptual solution architecture is complete and now informing the procurement of the solution
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Commence Build | Q3 2023-24 | Complete | Q3 2023-24 | Awaiting outcome of procurement activities
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Scope requirement and start design of video walls | Q4 2023-24 | On track |  | User requirements completed and design is underway. This design will be informed by the upcoming procurement PQQ. Working with epri to understand the control room of the future and how we can apply this to our environment
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Commence Solution Testing | Q1 2024-25 | On track |  | User requirements completed and now entering procurement phase for new hardware and software
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | ENCC Operator Console build complete. Move to implementation and enhanced testing | Q3 2024-25 | On track |  | User requirements completed and now entering procurement phase for new hardware and software
1 | Transform Network Control | D1.3.3 | Upgraded Control Centre video walls and operator consoles, with a single interface giving an overall state of the power system | Development and testing of user experience tools and video walls | Q4 2024-25 | On track |  | User requirements completed and now entering procurement phase for new hardware and software
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Enhanced Balancing data discovery & ingestion | Q3 2023-24 | Delayed - Internal Reasons |  | Regular consultations being held with the OBP team to align each team's roadmap. After re-prioritisation both teams have committed to new dates. Due to industry demands the OBP team is committed to delivering BM reserve in Summer 2024 causing the Audit data for DAP to move to later in the year. This work is now in design by the DAP team with a connection planned for May/June and Ingestion of an initial test dataset expected Summer/ Autumn 2024.
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Integrate data platform with enhanced balancing tool | Q4 2023-24 | On track |  | Consultation in November 2023 with OBP team. OBP wont need data in DAP until Autumn 2024 at the earliest
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Network Control tool data discovery & data ingestion | Q3 2024-25 | On track |  | Discussions held with Network Team in November to get latest progress update.
1 | Control centre architecture | D1.4.1 | Creation of a data and analytics platform that will act as the foundation for our new Control Centre architecture | Integrate data platform with new network control tool | Q4 2024-25 | On track |  | Awaiting plan and integration details of new network control tool
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q1 2023-24 | Complete | Q1 2023-24 | THE TAC meetings are happening quarterly as planned. After having an initial 2 year agreement with the members we have successfully renewed commitment from 95% to continue supporting us going forward. We are looking to utilise their advice further by creating additional sub groups for specific purposes
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q2 2023-24 | Complete | Q2 2023-24 | The TAC meetings are continuing to happen quarterly as planned. We had the first in person TAC this quarter.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q3 2023-24 | Complete | Q3 2023-24 | THE TAC meetings are happening quarterly as planned. Both the control room of the future sub group and the new Digital and data strategy met in this quarter.
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups Publication of annual report into the TAC's work and "you said we did" | Q4 2023-24 | On track |  | THE TAC meetings are happening quarterly as planned. After having an initial 2 year agreement with the members we have successfully renewed commitment from 95% to continue supporting us going forward. We are looking to utilise their advice further by creating additional sub groups for specific purposes
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q1 2024-25 | On track |  | THE TAC meetings are happening quarterly as planned. After having an initial 2 year agreement with the members we have successfully renewed commitment from 95% to continue supporting us going forward. We are looking to utilise their advice further by creating additional sub groups for specific purposes
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q2 2024-25 | On track |  | THE TAC meetings are happening quarterly as planned. After having an initial 2 year agreement with the members we have successfully renewed commitment from 95% to continue supporting us going forward. We are looking to utilise their advice further by creating additional sub groups for specific purposes
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups | Q3 2024-25 | On track |  | THE TAC meetings are happening quarterly as planned. After having an initial 2 year agreement with the members we have successfully renewed commitment from 95% to continue supporting us going forward. We are looking to utilise their advice further by creating additional sub groups for specific purposes
1 | Control centre architecture | D1.4.2 | Continue to facilitate meetings of the Technology Advisory Council (TAC) to advise the ESO on its system and technology transformation | Meeting of TAC and subgroups Publication of annual report into the TAC's work and "you said we did" | Q4 2024-25 | On track |  | THE TAC meetings are happening quarterly as planned. After having an initial 2 year agreement with the members we have successfully renewed commitment from 95% to continue supporting us going forward. We are looking to utilise their advice further by creating additional sub groups for specific purposes
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Initiate operational input into project scoping to enable operational visibility of DER (aligned with D15.8.2) | Q1 2023-24 | Complete | Q1 2023-24 | Operational input initiated with internal ESO stakeholders We have now performed test despatches with NGED based DERs and the system is now live
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into technical standards (aligned with D15.8.2) | Q2 2023-24 | Complete | Q2 2023-24 | The standards and discussion with MWD and NGED complete, we are still discussing some finer points with UKPN as they want to do something slightly different, but effectively the discussions are complete, what we are now discussing is small details in terms of how the process will work
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into IT discovery phase (aligned with D15.8.2) | Q3 2023-24 | Complete | Q3 2023-24 | Under Discussion - this is complete for NGED and is in the final phase with UKPN
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into IT discovery phase (aligned with D15.8.2) | Q4 2023-24 | On track |  | Under Discussion - this is complete for NGED and is in the final phase with UKPN
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into requirements and design phase to enable operational visibility of DER (aligned with D15.8.2) | Q1 2024-25 | On track |  | Linked to OBP project
1 | Operational coordination with DER and DSO | D1.5.1 | Increased DER visibility in real-time operations | Provide operational input into delivery of DER data into the Control Centre | Q4 2024-25 | On track |  | Tied to OBP project
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into IT discovery phase (as ref in 15.8.3) | Q1 2023-24 | Complete | Q1 2023-24 | Operational input being provided into MW dispatch project - implemented with NGED, advanced discussions with UKPN and ongoing discussions with UKPN
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into completion of IT discovery phases and costs (as ref in 15.8.3) | Q2 2023-24 | Complete |  | complete
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into primacy rule enhancements and further use cases. Provide operational engagement with DER service providers on operational impact of primacy rules. | Q4 2023-24 | On track |  | Now supporting DER visibility manager along with connecting to DNO control room managers to widen debate.
1 | Operational coordination with DER and DSO | D1.5.2 | Whole electricity system operational service coordination | Provide operational input into primacy rule enhancements and further use cases. Provide operational engagement with DER service providers on operational impact of primacy rules. | Q4 2024-25 | On track |  | Now supporting DER visibility manager along with connecting to DNO control room managers to widen debate.
1 | Operational coordination with DER and DSO | D1.5.3 | Development of RDP and LCM functionality into real-time environment | Continue to provide operational input into LCM and RDPs | Q4 2023-24 | On track | Q4 2023-24 | LCM is still in early development stages but trials are proceeding. We are now live and LCM is being embedded into ENCC process
1 | Operational coordination with DER and DSO | D1.5.3 | Development of RDP and LCM functionality into real-time environment | Continue to provide operational input into LCM and RDPs | Q4 2024-25 | On track |  | LCM is now live, and being embedded into ENCC process
1 | Operational coordination with DER and DSO | D1.5.4 | Increased operational liaison | Establish a forum and ToR for operational flexibility service coordination with DSOs | Q1 2023-24 | Complete | Q1 2023-24 | Operational forum established with DNOs to facilitate operational discussions, bilateral discussions take place on specific service co-ordination issues (for example LCM/MW dispatch)
1 | Operational coordination with DER and DSO | D1.5.4 | Increased operational liaison | Deliver new meetings | Q2 2023-24 | Complete | Q3 2023-24 | Complete - continue to update for next quarter
1 | Operational coordination with DER and DSO | D1.5.4 | Increased operational liaison | Continue with regular meetings | Q4 2024-25 | On track |  | In progress
1 | Minimising Balancing Costs | D1.6.1 | Constraint boundary optimisation | Achieve coverage of additional constraint management role in Control Centre | Q3 2023-24 | Complete | Q3 2023-24 | Discussion ongoing as to how best to incorporate this role into the ENCC, possibly as part of a new DAS team
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Programme plan shared | Q1 2023-24 | Complete | Q1 2023-24 | Balancing Costs Strategy has been shared with Incentives Performance Panel and Ofgem
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Updated programme plan shared | Q3 2023-24 | Complete | Q3 2023-24 | Balancing Costs Strategy has been shared but more detail to be added following stakeholder engagement
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Updated programme plan shared | Q1 2024-25 | On track |  | We plan to continue to develop and add detail to our balancing costs strategy
1 | Minimising Balancing Costs | D1.6.2 | An agile programme of strategic and tactical Balancing Cost improvement activities covering Roles 1, 2 and 3. | Updated programme plan shared | Q3 2024-25 | On track |  | In Progress
1 | Minimising Balancing Costs | D1.6.3 | Stakeholder Engagement on Minimising Balancing Costs | Regular sessions with stakeholders to discuss opportunities to minimise balancing cost. | Q2 2023-24 | Complete | Q2 2023-24 | We will be hosting stakeholder engagement sessions in Q2
1 | Minimising Balancing Costs | D1.6.3 | Stakeholder Engagement on Minimising Balancing Costs | Continuing Stakeholder Engagement forum on Balancing Cost Minimisation | Q4 2024-25 | On track |  | In progress
1 | Ongoing activities | D2.1.1 | Develop and drive control centre strategic resource planning, scheduling and training. | Fully staffed ENCC rota. Redesigned training schemes to facilitate needs of future ESO capabilities. New recruits direct entry from academia. | Q4 2023-24 | Continuous activity |  | The last campaign for 2023 has completed and we have now reached the end of year headcount. This campaign was based on roles that required NSV. We have a new campaign for 2024 to increase headcount by 8 FTE.
1 | Ongoing activities | D2.1.1 | Develop and drive control centre strategic resource planning, scheduling and training. | Fully staffed ENCC rota. Redesigned training schemes to facilitate needs of future ESO capabilities. New recruits direct entry from academia. | Q4 2024-25 | Continuous activity |  | Continued recruitment will be needed to meet the age profile and known attrition as well as the continued development of our staff and company. New training courses have been designed and delivered to existing trainees.
1 | Ongoing activities | D2.1.2 | Incident analysis and investigations of abnormal events, implementing improvements where needed. | The recommendations and actions from the incident investigation will help the ESO to operate the system more efficiently and securely. All root causes will be identified, and measures put in place to mitigate against any reoccurrence. Learnings shared with system users where applicable. | Q4 2024-25 | Continuous activity |  | On track – ESO has been consistently reviewing any significant incidents that had operational impact or significant near-miss events/incidents. Where applicable shared learnings are circulated with relevant parties.
1 | Ongoing activities | D2.1.3 | Monitoring and reporting of system performance to regulatory bodies. | All regulatory reports are created to time and quality. | Q4 2024-25 | Continuous activity |  | On track - System Performance Reports: All regulatory reports have been published on time. GC105 and GC151 monthly System Incidents are reported on the ESO website. ESO has recently published the annual report of C17 NETS Performance, ICS (Incident Classification Scale), LFC (Load-frequency Control) and CEP (Clean Energy Package) Article 13 - Redispatching. https://www.nationalgrideso.com/industry-information/industry-data-and-reports/system-performance-reports
1 | Ongoing activities | D2.1.4 | Guidance on operational policies for use in the control centre produced. | The guidance is unambiguous and the information are kept up to date. | Q4 2024-25 | Continuous activity |  | On track - Control Centre has the most accurate information readily available, is unambiguous and information are kept up to date.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Deliver work based placement years | Q1 2023-24 | Complete | Q1 2023-24 | 12 one year Industrial placements have been issued. 5 for power system engineering, 3 for commercial analysts and 4 for data scientist. All are due to start with the ESO in from July 2023 and come from a wide range of UK universities.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Deliver reviewed modules and year 3 placement opportunities defined | Q2 2023-24 | Delayed - Internal Reasons | Q3 2023-24 | Due to changes in personnel and the creation of the FSO we are behind on this action however we are establishing a relationship with Loughborough College to continue the development of our Apprenticeship Training Scheme as well as forming a University Steering group headed up by our Chief Engineering. We also continue working relationships with Brunel and Manchester University
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Delivery of placement opportunities | Q3 2023-24 | Complete | Q3 2023-24 | We have 12 Industrial placement students who started with the ESO in July 2023. 4 of these are Power System Engineer Graduates.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Delivery of modules and receive feedback on placement opportunities | Q4 2023-24 | Delayed - Internal Reasons |  | Due to resourcing challenges in the operational teams we have been unable to continue the work we had started with academia. We have also seen a marked reduction in students studying power system management with some universities no longer offering the course.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Review and update summer placements for 2024 | Q1 2024-25 | Delayed - Internal Reasons | Q3 2023-24 | Summer placements - we are not in a position to offer these currently. They have been built into the early careers strategy for 2025 as they will support the feeder pipeline for apprenticeships.
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Update placement opportunities for one year placements | Q3 2024-25 | On track |  | On Track
1 | Enhanced training material | D2.2.1 | Development of new modules and (based on feedback) new qualifications in system operation formed via an enhanced partnership with academic institutions | Refresh and run existing courses | Q4 2024-25 | On track |  | On track
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Further develop cross industry secondments | Q1 2023-24 | Complete | Q1 2023-24 | We have discuss with some industry parties future cross industry secondments and found there to be little interest at this stage. The reason being stated are the constant resource challenges many are facing. We will continue to work with our current secondment organisations such as CORESO and BEIS whilst we explore this option further.
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Engage with selected DNOs with potential cross simulator training options | Q2 2024-25 | On track |  | On Track
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Develop requirements for connectivity of training simulators | Q4 2023-24 | Delayed - Internal Reasons |  | Training Simulation environments are expected to be delivered for UAT however the ability to connect to DNO's will be delayed. We are prioritising the stakeholder engagement with the DNO's to understand their technical requirements and how we connect together in the future,
1 | Enhanced training material | D2.2.2 | Enhanced training and simulation with DNOs and wider industry | Trial training DNOs in simulators | Q4 2024-25 | On track |  | On Track
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Initial NCMS Training Simulator Stood Up | Q2 2023-24 | Delayed - Internal Reasons |  | NCMS initial onsite delivery is delayed this has impacted on our ability to stand up the initial Training Simulator. Data Centre is available from October assumed 6 months post this to have a training simulator. However the Training Simulator is not required till October 24 to meet overall delivery timescales. As such a strategic decision has been made to move this delivery to June 24.
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Complete Requirements for Joint Training Simulator | Q4 2023-24 | On track |  | ESO project mandate in process being raised and requirement gathering formally beginning after this.
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Commence Dev/Test Phase | Q2 2024-25 | On track |  | Needs to be baselined against NCMS and OBP plans to align for delivery
1 | Training simulation and technology | D2.3.1 | Upgrades to current simulators, including annual scenario snapshot refreshes, ahead of developing new training simulation capability, including end-to-end bespoke training scenarios and simulated operational systems using live data. | Training Simulator Move to Implementation | Q4 2024-25 | On track |  | Needs to be baselined against NCMS and OBP plans to align for delivery
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | An initial suite of learning packages built | Q1 2023-24 | Complete | Q1 2023-24 | A number of learning packages have been designed and developed with more planned for Q2. This includes an increase in on-line training material and the use of simulated scenarios for Energy Balancing training. Including technical role training for Transmission roles which have been difficult to recruit to.
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | Learning packages tried and tested on trainees and amended where necessary | Q2 2023-24 | Complete | Q2 2023-24 | Training resources and material have been tried and tested on a number of new trainees with positive results. New training courses have been delivered for operational and non-operational staff. Feedback has been positive.
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | All staff requiring access to the training packages have easy access 24/7 | Q4 2023-24 | On track |  | Training packages created and stored in an area accessible to all staff. Used daily as part of the operational training courses.
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | A full comprehensive suite of learning packages available and new ones added regularly | Q1 2024-25 | On track |  | On Track
1 | Training simulation and technology | D2.3.2 | New training methods and platforms, including online and e-learning, introduced to support training and new starters and continued development of existing staff | All staff requiring access to the training packages have easy access 24/7 and are able to use simulation training remotely | Q4 2024-25 | On track |  | On Track
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Delivery of Automated System and Mobile App | Q1 2023-24 | Complete | Q1 2023-24 | Phase 3 is currently being assessed by internal and external IT providers with a number of future developments in the pipeline. The new automated system has now replaced the old manual system and the mobile app is being used by all operational staff.
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Develop document management and rota improvements | Q4 2023-24 | On track |  | Phase 3 requirements have been sanctioned and the statement of works has been submitted to the vendor. First release due January 24.
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Agile system that allows the user to register for training and receive training when it suits them | Q1 2024-25 | On track |  | Phase 3 requirements have been sanctioned and the statement of works has been submitted to the vendor.
1 | Workforce and change management tools | D2.4.1 | Personalised updates and automated shift logins to be made available on different platforms and updated to a user's profile, giving better training and operational decision making. | Implement document management and rota improvements | Q4 2024-25 | On track |  | Phase 3 requirements have been sanctioned and the statement of works has been submitted to the vendor.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Annual review of Training Plans | Q1 2023-24 | Complete | Q1 2023-24 | Annual review has been carried out on all the training plans associated to operational roles within the ENNC. They have been updated to include a skills matrix and links to newly delivered on-line learning.,
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Ad hoc review of training plans | Q2 2023-24 | Complete | Q2 2023-24 | All training plans and associated documents have been reviewed and updated to include links to online training and supporting documentation.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Ad hoc review of training plans | Q3 2023-24 | Complete | Q3 2023-24 | All operational training plans have been reviewed and updated with a detailed skills matrix and links to newly designed training packages.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Personalised training plans in place with continued gap analysis | Q4 2023-24 | On track |  | Personal training plans issued to all trainees and a detailed skills matrix/ gap analysis carried out between trainee, trainer and line manager.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Created automation of training plans | Q1 2024-25 | Delayed - Internal Reasons |  | Due to the time taken to sanction Phase 3 this work will be delayed however we are still confident that it will be delivered within 12 months.
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | User testing of automation system for training plans | Q2 2024-25 | On track |  | On Track
1 | Workforce and change management tools | D2.4.2 | Content and infrastructure for personalised training plans designed, developed and delivered. | Roll-out of automated training plans for Operational training | Q4 2024-25 | On track |  | On Track
1 | Ongoing activities | D3.1.1 | Control Centre has fully tested skills, processes, plans and tools to support incident management and disaster recovery. | Fully meeting existing requirements. Future scope needs to be confirmed, following the publication of the Electricity System Restoration Standard. | Q4 2024-25 | Continuous activity |  | On Track
1 | Ongoing activities | D3.1.2 | Restoration plans for GB with the necessary stakeholders, developed, maintained and validated. | Following the publication of the Electricity System Restoration Standard, first Assurance framework approved by Ofgem. Continue maintaining and validating fit for purpose Restoration Plans. | Q4 2024-25 | Continuous activity |  | On Track
1 | Ongoing activities | D3.1.3 | Engage and collaborate with industry to plan and develop the new GB restoration standard, including the annual assurance framework, consistent with our licence obligations. | Code Admin Consultation sent out to industry Draft Final Modification Report and Issued to Ofgem | Q1 2023-24 | Complete | Q2 2023-24 | FMR issued to Ofgem in September
1 | Ongoing activities | D3.1.4 | Advice and oversight of Restoration and restoration strategy for the future provided. | Following the publication of the Electricity System restoration Standard, first Assurance Framework approved by Ofgem. | Q4 2024-25 | Continuous activity |  | On Track
1 | Ongoing activities | D3.1.5 | Fully competitive Restoration procurement process with submissions from a wide range of technologies connected at different voltage levels on the network, with DNOs playing a more active role in the restoration approach. | In 2023/24 technical evaluation and assessment of SE and Northern tenders. Award contracts for SE and Northern (and Wind) restoration services. | Q4 2023-24 | On track |  | On Track
1 | Ongoing activities | D3.1.5 | Fully competitive Restoration procurement process with submissions from a wide range of technologies connected at different voltage levels on the network, with DNOs playing a more active role in the restoration approach. | In 2024/25 new Tenders to meet requirements for ESRS implementation. | Q4 2024-25 | On track |  | On Track
1 | Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance framework for Electricity System Restoration | Review, update (if required) and submit for Ofgem's approval the annual Assurance Framework | Q1 2023-24 | Complete | Q1 2023-24 | Assurance Framework for 2023/24 was submitted to Ofgem on 14 April 2023
1 | Restoration standard | D3.2.1 | Facilitate and compile, on behalf of the GB industry, the annual assurance framework for Electricity System Restoration | Review, update (if required) and submit for Ofgem's approval the annual Assurance Framework | Q1 2024-25 | On track |  | On track
1 | Restoration standard | D3.2.2 | Validate restoration timelines for GB using the assurance data. | Electricity System Restoration will become a much more agile process, featuring swift methodical power supply recovery and a whole system approach with the appropriate system control, simulation and decision making tools in place. | Q4 2024-25 | Continuous activity |  | On Track
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Update regulatory framework following Ofgem's approval of regulatory changes | Q1 2023-24 | Delayed - Internal Reasons | Q4 2023-24 | Regulatory Framework Updates are with Ofgem for approval, 10 days after approval by Ofgem, the published copies of the regulatory framework would be updated to reflect the approved changes
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Engagement with industry to ensure progress with network changes. | Q2 2024-25 | On track |  | On track
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Engagement with industry during tender process to secure restoration service providers | Q3 2023-24 | Complete | Q3 2023-24 | There has been extensive stakeholder engagement on the Tenders launched in 2023
1 | Restoration standard | D3.2.3 | Maintain obligations and requirements against the new standard for restoration capability provision | Engagement with industry for training and upskilling. | Q3 2024-25 | On track |  | On track
1 | Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations and licence obligations. | Tool available for integration with Network Control programme | Q4 2023-24 | Delayed - Internal Reasons | Q2 2024-25 | Resourcing issues - unavailability of specialist resource over the summer, in ESO IT team has introduced delays to the delivery of the RDST
1 | Restoration standard | D3.2.4 | Restoration decision making support tool designed and developed to aid faster restoration times in line with stakeholder expectations and licence obligations. | Further tool testing and continuous development. | Q4 2024-25 | On track |  | on track
1 | Innovation project in restoration | D3.3.1 | Trial case studies based on different technology types in the Distributed ReStart innovation project. | Third Power Engineering live trial (including testing of Distributed Zonal Controller) | Q3 2023-24 | Complete | Q3 2023-24 | Complete
1 | Innovation project in restoration | D3.3.2 | Subject to industry adoption, Distributed ReStart proof of concept findings implemented and new system and communication methods implemented | We will fully understand Distributed ReStart's final recommendations and their implications. | Q1 2023-24 | Complete | Q1 2023-24 | Recommendations from Distributed ReStart are being implemented as part of ESRS
1 | Innovation project in restoration | D3.3.2 | Subject to industry adoption, Distributed ReStart proof of concept findings implemented and new system and communication methods implemented | We will have made decisions on which recommendations will be implemented in future (subject to industry adoption) | Q3 2023-24 | Complete | Q3 2023-24 | Selected recommendations from Distributed ReStart are being implemented as part of the tender process
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q1 2023-24 | Complete | Q2 2023-24 | Published 6 July 2023 after a short delay to ensure content is complete and up to date
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q3 2023-24 | Complete | Q3 2023-24 | We have reviewed activities across the ESO to identify those which contribute to the ongoing delivery of transparency for the ESO and produced the revised ESO Transparency Roadmap, published 21st December
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q1 2024-25 | On track |  | Actions required have been diarised to avoid another delay
1 | Ongoing activities | D17.3 | Transparency Roadmap | Publish Transparency Roadmap refresh. | Q3 2024-25 | On track |  | Actions required have been diarised to avoid another delay
1 | Ongoing activities | D17.6 | ESO Operational Transparency Forum (OTF) | Weekly OTF held to provide timely operational insight and an opportunity for question from industry. Positive stakeholder feedback received. | Q4 2024-25 | Continuous activity |  | The OTF continues to be held weekly with active participation from industry stakeholders. in December we issued a survey to all external and internal stakeholders . We asked how well the current approach meets their needs and what changes they would like to see. This will identify and drive continuing improvements to these events. We have committed to share the survey outcomes at an OTF in January 2024
1 | Ongoing activities | D17.7 | Proactively driving transparency in ESO decision-making through identification, prioritisation and publication of more datasets and insight communicated through the Transparency Roadmap | Provides industry with greater transparency of our decisions in areas of high significance to stakeholders. | Q4 2024-25 | Continuous activity |  | We continue to engage with stakeholders to explain how the ESO makes dispatch decisions and to respond to queries arising from the data published each week. On 2 June we held our first Online Dispatch transparency event attended by over 300 stakeholders. We have also presented at the Balancing Programme Quarterly event on 15 June and engaged with customers bi-laterally. In cooperation with the work on Enhancing Flexible Storage in the Balancing Mechanism we are investigating opportunities to make the Dispatch Transparency dataset more accessible to ensure analysis and insights can be made to identify potential improvements for ESO processes and customer business models.
1 | Ongoing activities | D17.8 | Digital Engagement Platform (DEP) continued phased deployment | The DEP will make the experience of engaging with the ESO more intuitive and user friendly by providing a single sign on for all ESO services and a personalised user experience with access to information, data and other services including markets, connections and codes. | Q4 2024-25 | Continuous activity |  | Progress made: Following the successful deployment of the Digital Experience Platform at the end of March 23, the DEP Programme has delivered a number of smaller agile releases including enhancements to Asset Management and Content search as well as enabling features for the single sign on capability. DEP has continued to deliver incremental releases with a major release of the CIAM capability for SMP, EAC, Data Portal subscriptions and notifications successfully completed at the start of Q3FY24 and CIAM Integration with Connections Portal on 5th Dec 2023 alongside enhancements for HND Maps. This release merged the SMP/Connections Portal duplicated records and hence reduced the number of duplicated users and simplified the custoemr journey for those users. Post go live there were 3 ESO website incidents which require fixing Pre-Christmas. Release 3.1 and 4 in development and ready for release by Jan and March 2024. This will give improvements towards notifications and personalization and CIAM PODE Integrations. Working with Salesforce team for implementing Long term solution before PODE Integration.
1 | Ongoing activities | D17.9 | Open Data Catalogue | Provides external users with a view of ESO Data and enables internal users to develop their own data products to benefit consumers. | Q4 2024-25 | Continuous activity |  | Initial integration with Catalogue tool, undergoing assessment to identify when new tool features can be deployed
1 | Ongoing activities | D18.1.1 | Daily analysis of Market activity and transaction data | Robust process for analysing data in a timely manner, which allows us to identify any suspicious behaviour. | Q4 2024-25 | Continuous activity |  | The market monitoring team have a daily process established to review dynamic data, prices, and physical notifications of all balancing mechanism units. All potential suspicious activity or inconsistencies in data are logged and reviewed by the team to determine the next steps of an alert or investigation. The team has an on-going innovation project working on producing sophisticated alerting to generate additional alerting for the team to review on a daily basis. The first and second work pack activities have been completed with the third very nearly finished. Outputs from the first two stages of this project have been implemented into the team's daily process. Power BI dashboards have been produced to support longer term trends of behaviour and to assess suspicious activity in relation to a particular element of REMIT or market rules.
1 | Ongoing activities | D18.1.2 | Detection of suspicious behaviour and submission of Suspicious Transaction Reports (STR) to Ofgem | The continuous submission of detailed STRs to Ofgem, in a timely manner over the course of BP2 | Q4 2024-25 | Continuous activity |  | Alongside the data based alerts via the automated tool assessing balancing mechanism data and Power BI dashboards, the team have established communication channels via email .box's to receive both internal to the ESO and external queries or tip-offs regarding potential suspicious activity. Every alert is assessed against REMIT and market rules and where there is reasonable grounds of suspicion of a breach of REMIT following an investigation, a suspicious transaction report (STR) will be created and shared with Ofgem's REMIT team. Similarly, where there is suspicion of a breach of market rules, a market incident report (MIR) is created. In quarter three, the team has submitted one STR. All timings of STRs are tracked and have been submitted within ACER's 28 day guidance.
1 | Ongoing activities | D18.1.3 | Undertake independent review of our Market Monitoring compliance activities against our PPAT and licence obligations alongside emerging market services. | This process includes a review of the original risk assessment and additional risk assessments of new market products and services. | Q4 2024-25 | Continuous activity |  | The market monitoring team conducted a refresh of all risk assessments for existing and new market products and services in March 2023 to evaluate the risk of market manipulation. As part of this process, trend analysis was completed to assess the costs, volume and competitiveness of the balancing services to inform the decision making of the risk assessments. The team has undertaken trend analysis of all balancing services that were identified as at least amber risk of market manipulation in the risk assessments conducted in March 2023 to assess anomalies across the last 6 months and investigate those incidents in greater detail for market manipulation. The team commissioned an independent external review of the design and operating effectiveness of the team's processes to identify strengths and areas of improvement. This review has been completed with a report produced sharing the findings and opportunities for the future. The report expressed that the market monitoring team had attained a high standard of practice in a short period. The market monitoring team has assessed each of the recommendations and determined a corresponding action with the majority of actions produced being implemented within FY24.
1 | Ongoing activities | D19.1.1 | Data and Analytics (D&A) Operating Model | Our D&A operating model brings together people, process and technology to enable the continuous development and enhancement of D&A tools across the ESO & ongoing publication of data to external stakeholders via our Open Data Portal. The Operating Model is comprised of i) a "Hub" team, setting the "rules and tools" for data product development and includes Data Governance, Data Operations & Data Stewardship, and ii) business "Spoke" teams, who work with the Hub team on our DAP platform to create new data products in a self-serve manner. | Q4 2024-25 | Continuous activity |  | continuous development is being undertaken to implement the operating model with an upgraded architecture planned
2 | Manage existing balancing services and markets | D4.1 | We manage an end-to-end process to ensure that balancing services are procured to deliver security of supply to lowest cost to consumers. | continued management of end-to-end processes | Q4 2024-25 | Continuous activity |  | this is an ongoing activity
2 | Manage existing balancing services and markets | D4.1.1 | Frequency management strategy | Delivery of FRCR report with enhanced look-ahead. | Q4 2023-24 | On track |  | Work is progressing well to set a clear scope for FRCR 2024, then modelling will begin and strategy will be developed.
2 | Manage existing balancing services and markets | D4.1.1 | Frequency management strategy | Delivery of FRCR report with enhanced look-ahead. | Q4 2024-25 | On track |  | scoping for this years version progressing well
2 | Power Responsive | D4.2.1 | Regular and specific metrics and publications across Distribution System Operator (DSO) development and co-development of local flexibility markets through a variety of innovation projects | Annual Report published | Q1 2023-24 | Complete | Q1 2023-24 | Report published
2 | Power Responsive | D4.2.1 | Regular and specific metrics and publications across Distribution System Operator (DSO) development and co-development of local flexibility markets through a variety of innovation projects | Annual report published | Q1 2024-25 | On track |  | Report on track for 24/25
2 | Power Responsive | D4.2.2 | Regular and specific metrics, and publications for multi sector approaches focusing on opportunities for household, community energy, small business participation, zero carbon technologies, and electrification of heat in Demand Side Flexibility (DSF). | Successful delivery of sector specific events and engagement to raise the awareness of ESO/DSO flexibility markets with the demand side community | Q4 2024-25 | Continuous activity |  | A number of smaller events are being held with the Power Responsive team including a summer event which is being held in London in July. 21/09/2023 PR have atteneded multiple external events and also held our PR Annual event on 18/09/2023 Update 15/12/2023 Power Responsive ran our annual event in august which we feel was very successful. Average BI score 8.3 with lots of good feedback. We also attended both BigZero and EMEX, at the latter we sponsored and controlled the large stage where we discussed various key topics. on 11th Dec we held our follow up Operational metering group where we were able to share the news on the extension of the Live Small Scale aggregated asset trial live in BM. We continue to support industry on the MIR challenge and have also started the I&C review. Kicked off the Annual Report scheduled for April24.
2 | Deliver an efficient frequency market | D4.3.3 | New reserve products - development and introduction of a new suite of products to provide reserve to the Control Centre | Launch Firm market for nBM providers (dependency on D4.3.5) | Q3 2023-24 | Delayed - Internal Reasons |  | A nBM market for Quick & Slow Reserve will be delivered after the OBP Strategic nBM functionality is released. This is planned to be Q2/Q3 25/26, engagement with industry is planned for co-creating the design of the services.
2 | Deliver an efficient frequency market | D4.3.3 | New reserve products - development and introduction of a new suite of products to provide reserve to the Control Centre | Launch Firm market for BM providers (dependency on OBP delivery) | Q4 2024-25 | On track |  | BM Market for Quick Reserve will be delivered in Q2/3 24/25 once the functionality has gone live on the OBP. BM Market for Slow Reserve is planned for delivery in Q2/Q3 25/26.
2 | Deliver an efficient frequency market | D4.3.4 | Delivering an efficient frequency market | Created longer-term procurement strategy which spans response and reserve looking at how the products interact with each other operationally and commercially, and the wider market. | Q4 2024-25 | Continuous activity |  | ESO are in the process of internally reviewing potential day 2 roadmap options. ESO recognise that the delay of our reserve products will impact the development of these activities as per the BP milestone. The go live of our response services has been positively received by industry allowing new functionality such as stacking and splitting as well as enhanced bidding options like negative pricing.
2 | Deliver an efficient frequency market | D4.3.5 | Auction capability | Implementation of the enduring auction capability and transition of the newly introduced services of BP1 onto the platform. | Q4 2024-25 | Continuous activity |  | EAC Article 18 EBR consultation was approved by ofgem on 13 October with the first auction running successfully on 2 November. Early operation of the new setup has seen all features being utilised by market participants including aspects such as negative bid prices. ESO have also seen reductions in our overall spend for the services operating on the platform and we will continue to monitor this and report findings accordingly. ESO has received widespread positive feedback about the go live of EAC and the extra functionality it provides participants particularly around the ability for bidders to stack services. We are reviewing and assessing day 2 road map focus areas and will share these in due course with industry.
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | In line with our new approach to annually consult on the new response services, we expect to formally engage with industry through the EBR Article 18 process in summer 2023-24. | Q2 2023-24 | Complete | Q2 2023-24 | Release 2 (2023-24) Electricity Balancing Regulation (EBR) consultation launched in Summer 2023 and will be submitted to Ofgem end of September 23. Key topics of focus for 2023-24 include removing barriers to Data-derived metering (baselining), clarity on topics such as State of Energy, updates to ramp rates, as well as a range of changes to tools and improvements to enable the Control Centre to operate the electricity transmission system securely.
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | We expect to publish updated service terms towards the end of Q3 2023-24. These changes will then feed into the C16 consultation process. | Q3 2023-24 | Delayed - Internal Reasons |  | Service terms will be updated and published following Ofgem approval (expected in Q4). Delay due to amendments required in drafting of revised Release 2
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | Working on the assumption that the annual cycle is welcomed by industry we expect to be consulting via the EBR Article 18 process on response services in Q2 2024-25. | Q2 2024-25 | On track |  | On track
2 | Deliver an efficient frequency market | D4.3.6 | Future developments to frequency response services | If we consult in Q2 2024-25, we expect to publish updated service terms towards the end of Q3 2024-25. These changes will then feed into the C16 consultation process. | Q3 2024-25 | On track |  | On track
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Initial integration with Enduring Auction Capability | Q2 2023-24 | Complete | Q1 2023-24 | SMP has delivered initial integration with the Enduring Auction Capability in Q1 to facilitate market trials in September and go live of EAC in October 2023
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Query Management process aligned with wider ESO digital process | Q3 2023-24 | Delayed - Internal Reasons |  | SMP will support a consistent query management process across the ESO. The Digital Experience team (DEP) showcased their latest design in the SMP Show and Listen Event on 15 June 2023 but the delivery of this process into production has been delayed past Q3, likely into Q1 or Q2 2024/25. The wider "Query Management" and "Help Centre" architecture will now be implemented from a central ESO Salesforce project rather than DEP. The DEP project will govern the delivery to drive consistency for users across multiple platforms. Change in approach to Salesforce has resulted in delay in starting dev work. Awaiting approved solution prior to estimation & scheduling.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Integration with Settlements system | Q4 2023-24 | On track |  | SMP is targeting initial integration with the new STAR system from Q4 2023/24. In the SMP Show and Listen event on 07 September we canvassed opinion from the industry on what they want NGESO to focus on initially. As a result we are looking to providing visibility and downloading of invoice data and potentially to offer an associated API. We shall seek further user feedback through the rest of BP2
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | Enhance the wider BM registration process | Q2 2024-25 | On track |  | SMP was initially expecting to accelerate this activity into 2023/24 but the interaction with CNI data means that we are reverting to the original timetable. It is hoped that the majority of BM Registration will be managed through the SMP portal in the future.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.1 | A market platform through which market participants will be able to participate in balancing markets. | All balancing services procured through SMP | Q4 2024-25 | On track |  | SMP is initially focussed on new and enduring day ahead markets as well as tactical markets as required. We will introduce other markets to SMP as appropriate through BP2
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Supported the development of a proof of concept for industry asset register | Q2 2023-24 | Complete | Q3 2023-24 | ESO is actively working with UKPN and Electralink to develop a proof of concept that will see both SMP and the DNO share high level information with Electralink and they will share "risk of conflict" information to the opposite party where any MPAN match is found. Any matched data will inform SMP / UKPN users about assets pre-qualified for balancing services that may be committed elsewhere for a DNO service / behind a flexible DNO connection. We believe that this is a step beyond focusing on asset registry and the approach has been accepted by the Open Networks Primacy Technical Working Group in November 2023. We expect to conduct the PoC in Q4 2023/24 and provide feedback and learnings to the industry afterwards. This work will feed into the wider "DER Visibility" project within the ESO.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Participation in proof of concept for industry asset register | Q4 2023-24 | On track |  | ESO is actively working with UKPN and Electralink to develop a proof of concept that will see both SMP and the DNO share high level information with Electralink and they will share "risk of conflict" information to the opposite party where any MPAN match is found. Any matched data will inform SMP / UKPN users about assets pre-qualified for balancing services that may be committed elsewhere for a DNO service / behind a flexible DNO connection. We believe that this is a step beyond focusing on asset registry and the approach has been accepted by the Open Networks Primacy Technical Working Group in November 2023. We expect to conduct the PoC in Q4 2023/24 and provide feedback and learnings to the industry afterwards. This work will feed into the wider "DER Visibility" project within the ESO.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Integrate SMP with industry asset register (subject to it being available) | Q2 2024-25 | On track |  | ESO is actively working with UKPN and Electralink to develop a proof of concept that will see both SMP and the DNO share high level information with Electralink and they will share "risk of conflict" information to the opposite party where any MPAN match is found. Any matched data will inform SMP / UKPN users about assets pre-qualified for balancing services that may be committed elsewhere for a DNO service / behind a flexible DNO connection. We believe that this is a step beyond focusing on asset registry and the approach has been accepted by the Open Networks Primacy Technical Working Group in November 2023. We expect to conduct the PoC in Q4 2023/24 and provide feedback and learnings to the industry afterwards. This work will feed into the wider "DER Visibility" project within the ESO.
2 | Deliver a single, integrated platform for ESO Markets | D4.4.2 | Common standards, including interoperable systems, a common data model and shared minimum specifications between ESO and other flexibility platforms as well as at the distribution level. | Improved DER asset visibility within SMP and / or wider NGESO platforms | Q4 2024-25 | On track |  | ESO is actively working with UKPN and Electralink to develop a proof of concept that will see both SMP and the DNO share high level information with Electralink and they will share "risk of conflict" information to the opposite party where any MPAN match is found. Any matched data will inform SMP / UKPN users about assets pre-qualified for balancing services that may be committed elsewhere for a DNO service / behind a flexible DNO connection. We believe that this is a step beyond focusing on asset registry and the approach has been accepted by the Open Networks Primacy Technical Working Group in November 2023. We expect to conduct the PoC in Q4 2023/24 and provide feedback and learnings to the industry afterwards. This work will feed into the wider "DER Visibility" project within the ESO.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.3 | Reforming markets to facilitate future growth of Distributed Flexibility technologies and models | Develop an ESO strategy to facilitate the growth of Distributed Flexibility. It will aim to understand the capabilities of distributed flexibility, their unique challenges in entering our markets, a defined vision for distributed flexibility in 2035, and a set of actions to reform our markets to facilitate their growth and participation. | Q4 2023-24 | Continuous activity |  | We have been gathering technical and commercial insights on a range of flexibility technologies, including distributed flexibility, in the Service Provider Capabilities Mapping project. We’re in the process of analysing existing research and feedback to categorise and prioritise market barriers for distributed flexibility in ESO markets. Over the remainder of this financial year, we’ll further refine our vision for distributed flexibility and create a plan to address these market barriers.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.3 | Reforming markets to facilitate future growth of Distributed Flexibility technologies and models | Align actions with Markets Roadmap and market reforms. Continue to refine the strategy, including further deep dives on specific issues as technologies and markets evolves. | Q4 2024-25 | Continuous activity |  | We are developing the distributed flexibility strategy in coordination with our Markets Roadmap as well as REMA options.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.4 | Facilitating market access for Distributed Flexibility | Understand the key technical and commercial barriers to distributed flexibility today and deliver prioritised short-term changes as per ESO strategy. Progress towards the delivery of SMP (as per A4.4). | Q4 2023-24 | Continuous activity |  | We continue to engage with the market and stakeholders and evolving our strategy around the development of flex markets including the delivery of SMP. Over the course of 2023-2024 we will be developing a flexibility strategy that will propose the direction we will be taking. Our Flex Strategy is nearing completion. Included in this is a review of stacking and key service requirements. We continue to progress this with industry stakeholders and have made some progress with the DNO's over a PoC for coordination/primacy rules.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.4 | Facilitating market access for Distributed Flexibility | Continue to identify and deliver changes required to faciliate distributed flexibility participation and coordinate with long-term Distributed Flexibiltiy Strategy. | Q4 2024-25 | Continuous activity |  | We continue to engage with the market to ensure that we can coordinate flexibility. this includes Open Networks, our own internal product development and moreover creating our plans for evolving market strategy and this will become more apparent over the summer of 2023. Our Flexibility strategy is nearing completion including a review of stacking and service requirements.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.5 | Ensure co-ordination of markets across the whole electricity system | Locational data available for all providers of flexibility services to facilitate DSO awareness. Further consideration on how flexibility should be coordinated across ESO-DSO for contractual and procurement processes. | Q1 2023-24 | Delayed - External Reasons |  | We continue to work with the industry to develop the information needed to provide locational data. this in part is linked to DER visibility , Operational Data Sharing and Primacy work under Open Networks- all of which are co-led by ESO. Work is being done now on provision of information to DSO during 2024, and DER visibility.
2 | Facilitate whole electricity system market access for distributed energy resources | D4.5.5 | Ensure co-ordination of markets across the whole electricity system | Continue to identify and deliver changes to support market coordination. | Q4 2024-25 | On track |  | We continue to work with Industry to develop the tools/changes needed to support market coordination. As mentioned before there are direct links to the work on Operational Data sharing/DER visibility to ensure that the right data is shared to achieve optimal outcomes for customers. this work continues and will do so over coming period, to ensure that we are seen to be progressing Open Networks which is essential for delivering a flexible energy system.
2 | Balancing and ancillary services market reform | D4.6.1 | Development of competitive approaches to procurement of stability. | Long-term procurement: Implement the findings of innovation project and build on learnings from pathfinders, develop the details of implementing enduring long term market based on the output from BP1. Short-term market: Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project. | Q4 2023-24 | On track |  | • On progressing the mid-term (Y-1) Stability Market, we have now opened an Expression of Interest (EOI) for market participants who wish to receive an Invitation to Tender (ITT) for the first Mid-term (Y-1) Stability Market delivery year, commencing 1st October 2025. This EOI has an early-bird deadline which has now passed, and the final EOI closes early in 2024. Simultaneously to asking for expressions of interest, we also launched - and have now concluded - an informal consultation on service design, contract terms and technical eligibility criteria for the Mid-term (Y-1) market. We have reviewed the valuable feedback provided by everyone as part of the EOI consultation and continued to engage in bilateral conversations with prospective providers. The key next step is finalising all material ahead of formally launching the Invitation to Tender early in 2024. • In parallel, we are continuing to finalise the Y-4 and D-1 initial market design and beginning to engage the relevant teams in ESO to understand what will be required to deliver these markets, and in what timescales this can be achieved. We are working closely with the Centralised Strategic Network Planning team to ensure that new system studies through CSNP are aligned and co-ordinated with the Long-term (Y-4) Stability Market. Furthermore, we are undertaking some analysis to derive the expected value through a Short-term (D-1) Stability Market to ensure it can be appropriately prioritised by ESO in the roadmap for ancillary service and system developments. Our delivery plans will be updated through the recently introduced Markets Roadmap monthly delivery plan updates. Alignment with ESO’s new balancing, auction, and settlement systems will be a fundamental enabler.
2 | Balancing and ancillary services market reform | D4.6.1 | Development of competitive approaches to procurement of stability. | Continuous improvement of long-term market design based on industry feedback. Run procurement process, if required depending on the system needs, so that the market participants have sufficient time to make informed business decisions on possible solutions and bidding approach. Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project | Q4 2024-25 | On track |  | Activity not due to start until FY 2024-25 but on track (Dec 23). Main update provided on parallel deliverable.
2 | Balancing and ancillary services market reform | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Long-term procurement: Implement the findings of innovation project and build on learnings from pathfinders, develop the details of implementing enduring long term market based on the output from BP1. Short-term market: Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project. | Q4 2023-24 | On track | Q4 2023-24 | Following the reprioritisation activity ahead of winter 22/23, work on a Reactive Power market was paused. This work is now being re-started with a new timeline and deliverables being planned.
2 | Balancing and ancillary services market reform | D4.6.2 | Development of competitive approaches to procurement of reactive power. | Continuous improvement of long-term market design based on industry feedback. Run procurement process, if required depending on the system needs, so that the market participants have sufficient time to make informed business decisions on possible solutions and bidding approach. Depending on outcome of innovation project in BP1, kick off implementation programme to deliver short-term market. Go-live date to be determined based on the outcome of innovation project. | Q4 2024-25 | On track | Q4 2023-24 | Following the reprioritisation activity ahead of winter 22/23, work on a Reactive Power market was paused. This work is now being re-started with a new timeline and deliverables being planned.
2 | Balancing and ancillary services market reform | D4.6.3 | Maximise participation in ancillary services | Exploring barriers to entry across the ESO ancillary services markets, identifying mitigating actions and working with industry to implement the changes needed to facilitate routes to market, and increase participation and liquidity of our markets | Q4 2024-25 | On track |  | A new project team has been set up to lead on this. Scoping for this activity began in Q2 2023-24, focus will be on promoting access for renewables but aligning with other projects considering barriers to entry.
2 | Balancing and ancillary services market reform | D4.6.4 | Local Constraints Market reform | Assess whether LCM should be rolled out across other zones. Assess whether other services should be rolled out on the 3rd party flexibility platform | Q4 2023-24 | Continuous activity |  | Assessment of LCM continues following commencement in 2023. Fixes to enable the market to encourage all types of participant will be focus in shorter term.
2 | Balancing and ancillary services market reform | D4.6.4 | Local Constraints Market reform | Assess whether LCM should be rolled out across other zones. Assess whether other services should be rolled out on the 3rd party flexibility platform | Q4 2024-25 | Continuous activity |  | On track
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Publish co-created guidance covering any rule changes and system and operational improvements, in collaboration with Ofgem, BEIS and industry, within 4 weeks of rules being set. | Q1 2023-24 | Complete | Q1 2023-24 | CM: > Guidance is being updated with: > specific focus on areas of feedback > a new section of “new for this year” to assist parties with understanding Rules changes. > slides requested by DESNZ to aid in policy conversations to ensure consistent messaging cross-party in response to emerging focus of questions. > EMR DB have published the Operational Plan and circulated to over 3,000 parties on 12 June 2023 > EMR customer events are scheduled to take place on 19 July (in-person) and 25th July (online) to launch this year’s CM process, with a focus on prequalification and rule changes. > The EMR DB team have been working to update the process for query management to achieve quicker SLAs, and undertaken cross training of team to enable more rounded advice. CfD: > The EMR DB published CfD guidance prior the application window opening for Allocation Round 5. The guidance included: > How customers should complete the application form if applying for a private network CfD agreement > How Floating Offshore Wind applicants should provide the supply chain plan > How Solar PV applicants should entered their Initial Installed Capacity Estimate. > Clear steps on how applicants could view their Allocation results (e.g. examples were added of how applicants can check for confirmation of an action in the system being completed). > Overall formatting of the guidance documents were updated to ensure there was a clear flow through of each section related to the CfD Allocation process. > Guidance changes were refined in consultation with Delivery Partners, DESNZ and Ofgem and draft guidance documents were reviewed by a select group of customers. > The EMR DB also engaged through: > An auction scenarios video distributed to customers shortly after the budget notice being for Allocation Round being published > The CfD Launch Event and the EMR DB led applicant readiness webinar in early 2023.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Commence the pre-qualification process, with customers benefitting from enhanced guidance | Q2 2023-24 | Complete | Q3 2023-24 | CM: Prequalification application window closes on 19 September. The team is busy providing support to Applicants, including responding to queries. During 7/8 September, the Portal was running very slowly - the DB identified the root cause, correct it and issued comms to stakeholders on 8 September.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Conclude the pre-qualification and disputes processes and prepare for the auctions | Q3 2023-24 | Complete | Q3 2023-24 | CfD: Ofgem upheld the DB's decision on all of the disputes submitted to them. We recognise however that Ofgem did not uphold the DB's position on every matter included in the disputes. CM: The Tier 1 disputes process finished on 28 November 2023. The Tier 2 process is currently happening, with a small number of disputes raised to Ofgem for decision.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Deliver the auctions and post-auction activities, including capturing key learning points with industry | Q4 2023-24 | On track |  | CfD: The DB has successfully completed the Auction Round 5 auction process. AR5 results were released to industry on 8 September 2023 CM: EMR DB have developed and are following a robust programme plan to track and monitor all relevant and required milestones in the auction cycle from publishing the Auction Guidelines in July 2023 to the delivery of the auctions and reporting the auction results in March 2024. Following completion of Prequalification in Q3, we are now working with customers to ensure Pre-Auction processes are completed and preparation for the Auctions planned in Feb 2024
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Publish co-created guidance covering any rule changes and system and operational improvements, in collaboration with Ofgem, BEIS and industry, within 4 weeks of rules being laid. | Q1 2024-25 | On track |  | CfD: Following completion of the AR5 Auction, the team carried out a customer satisfaction survey, where they received a very high score of 8.6/10, reflective of the ongoing approach to co-creation of guidance and use of webinars and videos to support participants. CM: This milestone is dependent on decisions regarding Rule changes, which the Delivery Body is actively supporting the Government and Ofgem with developing, and learnings from the current Auction. Once these are known, guidance will be updated in preparation for the next Auction.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Commence the pre-qualification process, with customers benefitting from enhanced guidance | Q2 2024-25 | On track |  | CfD: The Delivery Body is undertaking planning and activities in preparation for Auction Round 6, which will open for applications on 27 March 2024. CM: As part of the new portal development, an integrated guidance platform has been designed within Salesforce to link guidance directly to related portal processes. The DB had commenced a programme of work to review and update guidance to support use of the new portal and will also update with Rule changes made by DESNZ and Ofgem.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Conclude the pre-qualification and disputes processes and prepare for the auctions | Q3 2024-25 | On track |  | Delivery of these milestones is sequential and so this milestone will commence after the preceding one has concluded.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.1 | Continuation of Electricity Market Reform (EMR) Delivery Body obligations: We will deliver the prequalification and auction processes for the Capacity Market and qualification and allocation processes for Contracts for Difference (CfD). We will also deliver our agreement management obligations for the CM. | Deliver the auctions and post-auction activities, including capturing key learning points with industry | Q4 2024-25 | On track |  | Delivery of these milestones is sequential and so this milestone will commence after the preceding one has concluded.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Develop a clear process for capturing and assessing policy, rule and process improvements which draws on operational experience and industry feedback and feed this into CMAG and other relevant BEIS and Ofgem processes. | Q1 2023-24 | Complete | Q1 2023-24 | The EMR DB has developed and shared with Ofgem a process for how they will identify and undertake initial assessment of proposals and then progress them through CMAG. Further work is being undertaken internally to develop a standardised approach for impact assessments, based on experience with changes to date, which will then be discussed with delivery partners for their input.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Q2-4: Once established, we will run the improvement process on an ongoing basis, with key outputs timed to meet BEIS, Ofgem and CMAG timelines. | Q4 2023-24 | On track |  | The DB has identified a large number of potential changes that could be made to the CM Rules to improve clarity, processes and operations. However, in many cases the changes require greater clarity around the original policy intent and whether that continues to be appropriate, and so the DB is now working with other delivery partners to review these areas in more detail, before they become detailed change proposals. Where there are separable changes, the DB will work these up into proposals to take to CMAG.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Undertake informal review of the improvement process with industry, BEIS and Ofgem to identify ways to refine the approach. | Q1 2024-25 | On track |  | The improvement process has been successful in identifying 'pain points' through review of customer queries, operational experience and review of the Rules. However, as identified above, this is now being further developed through a holistic process across all delivery partners.
2 | Electricity Market Reform (EMR) Delivery Body | D5.1.2 | Continuation of EMR Delivery Body obligations: We work with BEIS, Ofgem and industry to identify, assess and implement policy, rule and process changes to further develop the Capacity Market and CfD mechanisms. We will also actively contribute to BEIS's Ten Year Review of the Capacity Market and their strategic policy development for CfDs. | Q2 - Q4: Implement process refinements and run refined improvement process from Q2 onwards | Q4 2024-25 | On track |  | This milestone is dependent on the outcomes of the one above relating to process improvements.
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Production of 2023 ECR | Q1 2023-24 | Complete | Q1 2023-24 | Report submitted to the Department of Energy Security and Net Zero on 31 May 2023
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Develop further enhancements to security of supply modelling to support the transition to net zero (e.g. impact of weather, limited-duration technologies, DSR, and European modelling) | Q4 2023-24 | On track |  | This milestone represents a well-established annual cycle of work. This year's projects are now underway and will be reported in the 2024 Electricity Capacity Report in line with the well-established process.
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Production of 2024 ECR | Q1 2024-25 | On track |  | This is a report that we produce each year and delivery plans are well established. Work begins around March 2024
2 | Improve our security of supply modelling capability | D5.3 | Use of enhanced modelling and more granular data sets to improve security of supply modelling | Develop further enhancements to security of supply modelling to support the transition to net zero (e.g. impact of weather, limited-duration technologies, DSR, and European modelling) | Q4 2024-25 | On track |  | This milestone represents a well-established annual cycle of work. The 2024/25 projects will be considered once the 2024 Electricity Capacity Report is completed
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Stakeholder engagement and modelling enhancements following first study published in 2022 | Q1 2023-24 | Complete | Q1 2023-24 | We published our first 2035 resource adequacy study in December 2022 in collaboration with AFRY. We have since invited input and feedback from expert stakeholders via in-person / virtual round tables and bilateral discussions. We are now on track to set out our next steps for these studies and how feedback has informed this. This will be published on our Resource Adequacy website
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Stakeholder engagement and modelling enhancements following first study published in 2022 | Q4 2023-24 | On track |  | We are committed to engaging with stakeholders in this work. We have already offered opportunity for stakeholders to provide input following the first study. We published an update in July 2023 and have set up an expert group to work with us on this.
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Production of capacity adequacy study | Q1 2024-25 | On track |  | We published our first 2035 resource adequacy study in December 2022 in collaboration with AFRY. We have since invited input and feedback from expert stakeholders via in-person / virtual round tables and bilateral discussions. We published the next steps on our website in July 2023. We expect to be working on the production of the next study in Q1 2024-25 with the study being published shortly after in Q2 2024-25.
2 | Long-term capacity adequacy | D5.4 | Building our long-term security of supply modelling capability | Stakeholder engagement and modelling enhancements | Q4 2024-25 | On track |  | We are committed to engaging with stakeholders in this work. Following the publication of the second study in 2024, we will continue to engage and work with stakeholders.
2 | Code management / market development and change | D6.1 | Continued facilitation of industry changes to the Grid Code, Connection and Use of System Code (CUSC), System Operator Transmission Owner Code (STC) and Security and Quality of Supply Standards (SQSS). Also, delivery of nationally driven regulatory change through the open governance process. | Other code changes identified by the ESO or raised by 3rd parties and RCRC | Q4 2023-24 | On track |  | We have started analysing the refreshed RCRC data and plan to produce a recommendation in 2024. Grid Code: GC0117 - CBA is complete and in our view is positive for consumers. The workgroup vote is taking place in january. Expect to meet 2027 implementation timeframe CM088 - the STC modification that followed on from GC0141 (9th August Power Disruption) has now been approved. Completing all the post 9th August changes that were requested. CM079 – Has now been sent to Ofgem for a decision following the November STC panel. Winter 2023/24 programme of work delivered to ensure appropriate changes are in place across the codes and frameworks where necessary (eg GC161) GC161 and GC162 have now been implemented. CUSC mods CMP413 - we continue to work proactively the workgroup to develop a solution and the WACMs that have been raised. CMP392 - this is currently with Ofgem for a decision. CMP376(Queue Management) – WACM7 has been approved and has been implemented. CMP330/374/414 (connection competition) – no change as awaiting Ofgem decision. Following stakeholder engagement the ESO identified a way to progress the change more quickly and has reflected this in its consultation response. CMP425 – we worked collaboratively with the workgroup and proposer to support developing a solution under urgent timescales and this is on track to be submitted to Ofgem at the time of writing. We have presented on an issue related to zoning at TCMF, and this has been raised as a formal CUSC modification (CMP419) and has started workgroups. A number of modifications have been raised in the past quarter and we continue to support development of these through the workgroup process.
2 | Code management / market development and change | D6.1 | Continued facilitation of industry changes to the Grid Code, Connection and Use of System Code (CUSC), System Operator Transmission Owner Code (STC) and Security and Quality of Supply Standards (SQSS). Also, delivery of nationally driven regulatory change through the open governance process. | Progress further code modification proposals as required in addition to wider programme projects | Q4 2024-25 | On track |  | to update in 24/25
2 | Code management / market development and change | D6.1.1 | Enable major net zero programmes - Offshore Coordination | Delivery of code modifications associated with implementation of the offshore project dependent on progression of offshore coordination programme | Q4 2023-24 | On track |  | The Sub-group to support the Electricity System Operator (ESO) in developing changes to the Transmission Network Use of System (TNUoS) charging methodology in relation to the OTNR was launched early 2023 and has now concluded. The overall focus of the group was to consider, discuss and provide input into developing the charging principles and subsequent methodology changes to support the ESO in creating a set of code modifications to facilitate offshore coordination and there are 3 live modifications currently in the formal governance process and 1 new modification being raised in the near future. CMP402 - raised in response to Ofgem’s final decision on Anticipatory Investment (AI) - to introduce changes to the current User Commitment provisions within Section 15 of the CUSC (currently at workgroup stage). CMP411 - raised to introduce Anticipatory Investment (AI) and a mechanism for the recovery of AI costs within the Section 14 of the CUSC (currently at workgroup stage). CMP419 – raised to review the existing generation zoning methodology to incorporate offshore assets connected as part of the Holistic Network Design (HND) to enable the wider tariff to be applied to offshore generators.
2 | Code management / market development and change | D6.1.2 | Enable major net zero programmes - Onshore Competition | Delivery of code modifications associated with implementation of onshore competition dependent on progression of onshore competition | Q4 2023-24 | Delayed - External Reasons |  | CATO modifications are in flight. These modifications aim to introduce the concept of Competitively Appointed Transmission Owners (CATO's) and Transmission Service Providers for the purposes of introducing Early Competition for the design, build and ownership of Onshore Transmission assets. Now that the CATO legislation has been approved by Parliament (which was initially causing delays to this deliverable), the code administrator consultation (CAC) can commence. The original aim was to bring all CATO mods to be bundled together for presenting to Ofgem in late March 2024 (Grid Code, CUSC, STC and SQSS CATO mods). A few concerns around legal text were raised at the Grid Code Review Panel on 14/12/23 (as there are interactions between the CUSC modifications, namely CMP403 and CMP404, and the Grid Code modifications, namely GC0159 and GC0156). It was therefore decided to postpone the code admin consultation of the CUSC CATO mods until a decision on GC0156 decision is made (due on 30/01/24). The current plan for the Grid Code CATO mod (GC0159) is to go to the February 2024 panel for its workgroup report. It will then go to CAC in March 2024, and will arrive with OFGEM on the 7th May 2024. This assumes approval at the February 2024 panel. The final modification report for the CATO mods CMP403 and CMP404 will also go to OFGEM 7th May for approval. The SQSS CATO mods are going to SQSS panel on Wednesday 24th January. The ask of SQSS CATO panel is to straight to CAC, and then submitted to OFGEM in March 2024. SQSS mods are therefore on track. The STC CATO modifications (CM86/87) are currently at CAC and are on course for the FMR to go to OFGEM in March 2024. STC mods are therefore on track.
2 | Code management / market development and change | D6.1.3 | Enable zero carbon operation - System Restoration | Delivery of code modifications to set equipment specifications | Q1 2023-24 | Delayed - External Reasons |  | Modification process has taken slightly longer than anticipated due to complexity of the arrangements required, and alternative options being submitted as part of the open governance code process GC148 Implementation of EU Emergency and Restoration Code Phase II - was approved by Ofgem on the 18th August. GC156 Facilitating the Implementation of the Electricity System Restoration Standard - As of August 2023 this is with the authority awaiting a decision STC modification - CM089 - CM089 : Implementation of the Electricity System Restoration Standard - is currently in workgroups SQSS modification GSR32 Implementation of the system restoration standard - is currently in workgroups
2 | Code management / market development and change | D6.1.3 | Enable zero carbon operation - System Restoration | Completion of code changes | Q2 2023-24 | Delayed - External Reasons |  | Modification process has taken slightly longer than anticipated due to complexity of the arrangements required, and alternative options being submitted as part of the open governance code process GC148 Implementation of EU Emergency and Restoration Code Phase II - was approved by Ofgem on the 18th August 2023 and is awaiting implementation. GC156 Facilitating the Implementation of the Electricity System Restoration Standard - is with the authority awaiting a decision currently expected 30th January 2024. STC modification - CM089/91 : Implementation of the Electricity System Restoration Standard - is with the authority awaiting a decision currently expected 30th January 2024 SQSS modification GSR32 Implementation of the system restoration standard - is with the authority awaiting a decision currently expected 30th January 2024
2 | Code management / market development and change | D6.1.3 | Enable zero carbon operation - System Restoration | Code changes implemented for ESRS to facilitate licence compliance which is required by Dec 2026 | Q4 2024-25 | On track |  | Modification process has taken slightly longer than anticipated due to complexity of the arrangements required, and alternative options being submitted as part of the open governance code process GC148 Implementation of EU Emergency and Restoration Code Phase II - was approved by Ofgem on the 18th August 2023 and is awaiting implementation. GC156 Facilitating the Implementation of the Electricity System Restoration Standard - is with the authority awaiting a decision currently expected 30th January 2024. STC modification - CM089/91 : Implementation of the Electricity System Restoration Standard - is with the authority awaiting a decision currently expected 30th January 2024 SQSS modification GSR32 Implementation of the system restoration standard - is with the authority awaiting a decision currently expected 30th January 2024
2 | Code management / market development and change | D6.1.4 | Enable zero carbon operation - Stability | GC0137 'Grid Forming' Grid Code modification - guidance document delivery | Q1 2023-24 | Complete | Q1 2023-24 | The Grid Forming best practice guide is now on the ESO website
2 | Code management / market development and change | D6.1.5 | Lead charging reform | Raise TNUoS modifications to facilitate charging reform | Q1 2024-25 | On track |  | TNUoS Taskforce is currently working through a number of sub groups regarding identified issues. The 'sub groups' are now in the process of clearly articulating the defects and creating solutions. To date 2 Modifications have been raised with a further one to be raised in Q1 2024. It is expected that a number of further Modifications will follow throughout 2024. Scaling Factors was presented at the Taskforce and has now been raised as a formal CUSC modification (CMP424) which is due to start workgroup in January 2024. Generation reference nodes has also been raised as a formal modification following development by the Taskforce, raised by SSE (CMP423). In addition CMP413, raised by EDF is progressing through workgroups and ESO are fully engaged in this process. The TNUoS 10year projection has also been developed alongside this modification to aid industry in making investment decisions. This was an extra piece of work that the ESO have done on top of the obligations within the CUSC.
2 | Code management / market development and change | D6.1.5 | Lead charging reform | Identify required code changes | Q4 2023-24 | On track |  | CMP408 (amending the notice period) is awaiting a decision from Ofgem alongside CMP415 which looks at the fixed period following the analysis carried out through the CMP408 workgroup and the Enduring Fixed BSUoS subgroup. This sub-group is now on pause as it was agreed to wait for a decision on the aforementioned modifications and collect further data before raising any more modifications. This sub-group has received really positive feedback for the discussion it provided across industry, and the analysis that was shared. CMP420 was raised by industry and we are working with the workgroup to support the proposer developing a solution.
2 | Code management / market development and change | D6.1.6 | Support Market Wide Half Hourly Settlement | Code modifications concluded | Q1 2024-25 | On track |  | A revised MHHS Programme plan with associated milestones was approved by Ofgem following extensive industry consultation in 2023. The code modifications relating to MHHS will be concluded in March-25 as part of the Settlement Reform Significant Code Review process.
2 | Code management / market development and change | D6.1.6 | Support Market Wide Half Hourly Settlement | Produce required CUSC legal text and modifications raised | Q2 2023-24 | Delayed - External Reasons |  | A revised MHHS Programme plan with associated milestones was approved by Ofgem following extensive industry consultation in 2023. The code modifications relating to MHHS will be concluded in March-25 as part of the Settlement Reform Significant Code Review process. Solution options for Transmission charging across the MHHS migration period are being considered and CUSC legal text will be drafted drafted to feed into the MHHS Significant Code Review process by the MHHS Programme milestone of Feb 2024.
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Regulatory priorities, system maintenance and functional backlog implemented | Q1 2023-24 | Complete | Q1 2023-24 | 22/6: Q1 regular system maintenance and backlog management in place
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | Enduring team established to maintain new system (Q2), System maintenance and backlog management (Q3), Regulatory priorities and customer improvements implemented (Q4) | Q4 2023-24 | On track
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | System maintenance, regulatory priorities, customer enhancements and functional backlog management | Q1 2024-25 | On track
2 | Industry revenue management | D6.3 | Continued managing, collecting and disbursing charges relating to the operation of the transmission system. Also delivering a refresh of charging and billing IT system and changes to the charging regime for CUSC. | System maintenance, regulatory priorities, customer enhancements and functional backlog management | Q2 2024-25 | On track
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | High Level Discovery | Q2 2023-24 | Complete | Q2 2023-24 | 22/6 - high level I/A provided for MHHS P210 file change.
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Impact Assessment & Agree Approach | Q3 2023-24 | Delayed - Internal Reasons |  | Approach to receipt of data for TNUoS Charging agreed under the sign-off of MHHS Change Request 32. Approach and timing of testing for this to be agreed between MHHS Programme, Elexon and ESO. Approach to process for management of disputes relating to BOAs agreed and solution will be reflected in MHHS BSC Legal Text. A full impact assessment of consequential impacts of MHHS has not been completed yet. For example, changes to Supplier Time of Use Tariff offerings and therefore consumer behaviour and their associated impacts to system balancing have not been fully impact assessed. This will be developed and monitored across the months up to MHHS migration (Apr-25) and across the MHHS Migration period (Apr-25 to Oct-26).
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and implement | Q4 2023-24 | On track |  | On Track
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q1 2024-25 | On track |  | On Track
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q2 2024-25 | On track |  | On Track
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q3 2024-25 | On track |  | On Track
2 | Industry revenue management | D6.3.1 | Market half-hourly settlement | Design, test and start implemention | Q4 2024-25 | On track |  | On Track
2 | Industry revenue management | D6.3.2 | TNUoS reform | High Level Discovery | Q1 2023-24 | Delayed - External Reasons |  | Revenue team has shortlisted defects (considered by TF) for review, and have allocated these to categories (to progress as packages of work), aiming to create a workstream plan using the categories. Still some uncertainty on taskforce generally as indiviudal regs may get consumed by tnuos taskforce output which makes it challenging to conduct any technical discovery work in this quarter.
2 | Industry revenue management | D6.3.2 | TNUoS reform | Impact Assessment & Agree Approach | Q2 2023-24 | Delayed - External Reasons |  | Delayed until completion of Milestone High level Discovery (which is an earlier milestone in teh overall delivery of this objective)
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q3 2023-24 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in teh overall delivery of this objective)
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q4 2023-24 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in teh overall delivery of this objective)
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q1 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in teh overall delivery of this objective)
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q2 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in teh overall delivery of this objective)
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q3 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in teh overall delivery of this objective)
2 | Industry revenue management | D6.3.2 | TNUoS reform | Design, test and implement | Q4 2024-25 | Delayed - External Reasons |  | Delayed until completion of Milestone Impact Assessment & Agree Approach (which is an earlier milestone in teh overall delivery of this objective)
2 | Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | We are working on our internal capability to ensure we set ourselves up best to be a code manager. This includes: • Working on Code Digitalisation to improve the usability and navigation of our codes • Further proactive engagement with industry parties proposing changes to the codes we administer, seeking to ensure these are clear and value adding / raised at the optimum time" • Further enhancing our chairing and project management capability to ensure we maximise the value of all our stakeholder engagements notably at modification Workgroups and code Panels • Continuous improvements to our reporting, ensuring this is clear and understandable | Q4 2023-24 | Delayed - External Reasons | Q4 2024-25 | We have begun a programme to design a process for the ESO to fulfil the role of code manager. We have presented to OFGEM on our thoughts and ideas around the code manager process and how we feel we could facilitate this change. This includes - strategic road map of ideas and process flow -presentation to OFGEM -feedback requested on our thoughts, ideas and process -overlaying our new process with some previous modifications to demonstrate the difference that would have been made if followed -presentation to CUSC and GC panel on our thoughts and ideas of code manager -Specific relevant training courses for the team provided by external facilitators - Further embedding on the job training and internal processes - Breakdown of the current code and team process and review areas for further improvement - Customer and Stakeholder engagement and feedback to further improve communication
2 | Transform the process to amend our codes | D6.4 | Change from a code administrator to a code manager. | We are working on our internal capability to ensure we set ourselves up best to be a code manager. This includes: • Working on Code Digitalisation to improve the usability and navigation of our codes • Further proactive engagement with industry parties proposing changes to the codes we administer, seeking to ensure these are clear and value adding / raised at the optimum time" • Further enhancing our chairing and project management capability to ensure we maximise the value of all our stakeholder engagements notably at modification Workgroups and code Panels • Continuous improvements to our reporting, ensuring this is clear and understandable | Q4 2024-25 | On track |  | To be updated in 24/25
2 | Work with all stakeholders to create a fully digitalised Whole System Technical Code by 2025 | D6.5 | Develop a single technical code for distribution and transmission that is focused on providing minimum standards to allow safe and secure operation of the electricity systems. | Prioritise and raise modifications as identified through example work | Q4 2023-24 | On track |  | Grid code modification focused on the the simplification and rationalisation of section OC2 of the grid code has been submitted and is a live modification. The digitalisation side of the project is currently progressing to plan
2 | Work with all stakeholders to create a fully digitalised Whole System Technical Code by 2025 | D6.5 | Develop a single technical code for distribution and transmission that is focused on providing minimum standards to allow safe and secure operation of the electricity systems. | Progress modifications | Q4 2024-25 | On track |  | Minimal Viable Product for the digitalisation work should be March 2024. Any further work needed will be assessed after the original role out. creation of a more efficient simplified code is in flight, with OC2 ready to be submitted as a modification in once GC0156 has been approved. Further sections of the code may need to wait for the ECR decision from Ofgem to land.
2 | Fixed BSUoS tariff setting | D6.7 | Enhanced delivery of the recommendation from the BSUoS taskforce around reducing the volatility of BSUoS forecasting. | Continued investment in our forecasting capability and build on our existing capability for BSUoS forecasting. | Q4 2024-25 | Continuous activity |  | 22/6 - Balancing cost model improvements: We are working with the Hartree Centre to investigate whether state-of-the-art machine learning techniques could be employed to improve our forecast of balancing costs. Wholesale electricity price is a key input to our model. We continue to investigate the best way to represent the forward curve of these prices in our model
2 | Digitalisation of codes | D6.8 | Implementation of digital solutions | Implementation has commenced | Q4 2023-24 | On track |  | The Digital Code management (DCM) project delivers the ESO the technology capability to make industry codes accessible and consumable for customers. It will transform customer experience for the code management process through: - Digitalisation of codes - Contextual guidance and relevance for customers - Provision of enhanced navigation capabilities - Greater clarity on relevant sections using metadata tagging, document and workflow management tools Project Progress to date: - Project setup/stakeholder engagement - Scoping - Industry Engagement & User Research - Requirement definition - Conceptual Solution Design
2 | Digitalisation of codes | D6.8 | Implementation of digital solutions | Implementation is complete | Q4 2024-25 | On track |  | update will be provided in 24/25
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Full assessment delivery areas | Q2 2024-25 | On track |  | Initial areas for assessment identified and early plans developed. We are seeking to align this work with key strategic industry objectives to drive most value from this process.
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Establish team to deliver assessment of frameworks | Q3 2023-24 | Complete | Q3 2023-24 | Team members started Nov-23 with one remaining vacancy to be filled in Q4 23-34 in line with resource requirements.
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Detailed workplan and stakeholder engagement | Q4 2023-24 | On track |  | Detailed workplan and stakeholder engagement plan being developed now team members have been onboarded.
2 | Whole electricity system framework reform | D6.9 | Whole electricity system framework assessment | Identify and raise or recommend changes | Q4 2024-25 | On track |  | Activity not yet due to start
2 | Net zero market reform programme | D20.1 | Net Zero Market Reform programme | Be a trusted Partner to BEIS, Ofgem and the wider industry in this space. Ensuring the right market reforms to achieve net zero efficiently is a hugely complex challenge, with many interdependencies and a raft of future uncertainties. | Q4 2024-25 | Continuous activity |  | We continue to be a trusted partner to DESNZ and Ofgem in the REMA process. We have developed our position on investment policy recently publishing our NZMR Phase 4 report. We are on track to deliver assessments of scheduling and dispatch by the end of the financial year.
2 | Setting the net zero cross border landscape | D21.1 | Cross-border strategy development | First phase of implementation fully initiated | Q2 2023-24 | Complete | Q2 2023-24 | By modelling the cross border conditions for a number of future scenarios, ESO better understands how the needs of the GB net zero power system can be supported by interconnection, which is expected to significantly increase in capacity. This analysis identified future risks and opportunities that create value specifically in term of adequacy, operability and system adequacy. These areas of work have been prioritised so the highest value items can be focused upon. The output includes the identification of further research and development work packages needed to further define the final solutions to implement A final draft for comment was shared with Ofgem and DESNZ in September 2023.
2 | Setting the net zero cross border landscape | D21.1 | Cross-border strategy development | Conclusions and recommendations reviewed to check if they are still relevant | Q4 2024-25 | On track |  | Activity not yet due to start, however proceeding tasks are on track.
2 | Setting the net zero cross border landscape | D21.1.1 | Strategic Engagement with EU | UK/ EU TSO cooperation channels will be fully opened and functioning well | Q1 2023-24 | Delayed - External Reasons |  | Until the Trade and Cooperation Agreement Working Arrangements is approved by the EC and DESNZ, it cannot be signed and implemented by ENTSO-E and GB TSOs. The Working Arrangements agreement will allow the formal re-engagement between GB TSOs and the EU TSOs. However, informal engagement is underway with ENTSO-E and EU TSOs in a number of key areas including North Sea Cooperation (inc Offshore and MPIs), interconnector ramping limits, operational harmonisation and IC flow control tools.
2 | Setting the net zero cross border landscape | D21.1.1 | Strategic Engagement with EU | Engagement established with new EU stakeholder groups | Q1 2024-25 | On track |  | The new EU/GB TSO engagement groups will be established by the joint ENTSO-E/ GB TSO TCA Working Arrangements Coordination Group, which will is set up by the TCA Working Arrangements. This is awaiting approval by the European Commission/ DESNZ. Pre-emptive informal cooperation has been started with a number of existing ENTSO-E groups including Inter Synchronous Area sub group (GB - EU operational interactions), Regional Group North Sea (Offshore and onshore Network planning) and direction engagement with the Secretariat is underway on Multi Purpose Interconnectors and establishment of the first joint sub group for Offshore arrangements..
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Draft Interconnector Framework shared with industry | Q1 2023-24 | Delayed - Internal Reasons |  | The ESO has released and RFI on interconnector frameworks External engagement will take place ahead of industry consultation. This was re-prioritised to allow other work within the team take place earlier this year such as NTC and DFS derogation.
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Ramping solution is SOGL compliant | Q2 2023-24 | Delayed - External Reasons |  | The ESO has been working with an external consultant (Baringa) to carry out a CBA for interconnector ramping. This CBA has helped shape the ESO recommendation, which is to reduce interconnector ramp rates from 100MW/Min to 50MW/Min. This recommendation has been presented to the workgroup. The workgroup will propose an alternative. Process steps outlined below. Delay to original timeline is due to interconnector requests for other areas to be considered. Workgroup consultation July 2023 Workgroup report September 2023 Code Administrator Consultation October 2023 Modification Report December 2023. Report to be issued to Ofgem Dec 23- await a decision from Ofgem. Decision date to be confirmed and will update ticket to reflect this. Work group work is complete as it stands
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Interconnector framework consulted upon | Q3 2023-24 | Complete | Q3 2023-24 | Interconnector Framework RFI is now out, closing 7th December
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Long-term ramping solutions are investigated | Q4 2023-24 | On track |  | Following the GC154 workgroup we will continue to work with the interconnector owners and EU TSOs to identify longer term arrangements.
2 | Enhancing cross border frameworks and markets | D21.2.1 | Continued facilitation of EU driven code changes into Great Britain market | Interconnector Framework implementation plan agreed Long-term ramping solution implementation started | Q4 2024-25 | On track |  | Will follow on from consultation in 23/24 24/25.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Agreed UK Position on Day ahead, actively negotiating with EU TSOs Agreed Interim solution to cross border balancing at UK and EU level. Increased amount of engagement with EU TSOs | Q1 2023-24 | Delayed - External Reasons |  | Day Ahead Capacity Calculation (DACC) delayed due to limited engagement from EU TSOs on Capacity Calculation. EU TSOs likely to need a definitive steer from the Specialised Committee of Energy (SCE) in order to commit resources to DACC. The focus of the SCE steer this year (2023) has been in relation to MRLVC (Multi Region Loose Volume Coupling), which is Day Ahead Capacity Allocation. Interim Cross Border Balancing (CBB): On hold due to limited appetite from EU TSOs for such a product. RTE (the French TSO) has indicated they do not have resources for this.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Draft UK Position on Intraday and Long Term. Continued development of Day Ahead arrangements | Q3 2023-24 | Delayed - External Reasons |  | Delayed due to limited engagement from EU TSOs on Capacity Calculation. UK and EU TSOs will prioritise Day Ahead timeframes over other timeframes (i.e. Intraday and Long Term).
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | UK position on enduring balancing options agreed with all relevant parties | Q4 2023-24 | On track |  | Cost Benefit Analysis of CBB options completed. Agreed plan with DESNZ and Ofgem over summer 2023 for industry engagement to publish results. Held CBB industry webinar on 19th October 2023 to disseminate results, which was well attended. Finalising internal close-down reports on this activity.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Interim solution being implemented pending recommendation from the specialised committee on energy | Q1 2024-25 | Delayed - External Reasons |  | Interim Cross Border Balancing (CBB): On hold due to limited engagement from relevant TSOs.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Noticeable step change in ESO to EU TSO relationships | Q2 2024-25 | On track |  | Attending more meetings in-person (e.g. MRLVC, IC ramping). Initiation of EU Harmonisation meetings (ISA or Inter-Synchronous Area) - monthly meetings alternately in-person and online, including Amsterdam in October 2023. Next planned in-person meeting in Brussels April 2024. These meetings provide a forum for ESO to raise issues of concern / interest from our side, and understand concerns and developments from connected EU TSOs. Bilateral meeting in Dublin between ESO and EirGrid in November 2023, following the UK-Ireland MOU on energy transition. Recent EU-UK TSO cooperation on MRLVC (Multi Region Loose Volume Coupling) technical questions (Feb - June 2023). Awaiting further direction on MRLVC following Specialised Committee of Energy (SCE) meeting in November 2023.
2 | Enhancing cross border frameworks and markets | D21.2.2 | Implementation of the TCA | Technical UK position agreed and negotiating with EU TSOs Enduring solution agreed at UK Level, ongoing negotiations with EU | Q4 2024-25 | On track |  | Awaiting further guidance following CBB CBA results.
2 | Enhancing cross border frameworks and markets | D21.2.3 | Enhancing interconnector operations and access to Great Britain markets | A review of existing interconnector operations in light of the transition to a highly interconnected system. Consider cross border roles within future GB ancillary services markets. | Q4 2024-25 | Continuous activity |  | Underway
3 | Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | Undertake enhancements to ETYS Annual Report in response to stakeholder feedback. | Q1 2023-24 | Complete | Q1 2023-24 | The Annual ETYS consultation was completed on 15th May 2023 and we submitted the proposed Form of ETYS 2023 to Ofgem on 1st June 2023. This includes proposed improvements to the document based on feedback received over the past year.
3 | Analyse and communicate future network needs | D7.1 | Electricity Ten Year Statement (ETYS) | ETYS Annual Report Published part of the Transitional Centralised Strategic Network plan Year-round Thermal needs published in ETYS Voltage screening results in ETYS | Q4 2023-24 | On track |  | ETYS 2023 was successfully published on 29th August 2023. For the first time this year we have successfully brought forward publication of core content to allow our stakeholders more time to review system needs in advance of the Cost Benefit Analysis. The publication includes year-round thermal analysis and our voltage screening results in line with our commitment to expand our system needs. On 30th November we published ETYS appendix A (Existing Network diagrams), E (Fes charts), F (Contracted Generation), G (Nodal Demand), H (further information) and I (Transmission losses). We received a direction from Ofgem allowing us to delay the ETYS technical appendices B, C, D which contain future network data to align with the TCSNP2 publication in March 2024.
3 | Advise on economically efficient ways to address networks needs | D7.2 | NOA Annual Report | Start Engagement with Ofgem on the long-term requirement for Interconnector Analysis | Q1 2023-24 | Complete | Q1 2023-24 | We have started ongoing engagement with Ofgem in relation to our interconnector analysis for both the NOA and Cap & Floor Window 3.
3 | Advise on economically efficient ways to address networks needs | D7.2 | NOA Annual Report | Approval of Revised NOA Methodology | Q3 2023-24 | Complete | Q3 2023-24 | The draft methodology submitted to Ofgem on the 30th June 2023 has been has now been approved by Ofgem. This is now complete
3 | Advise on economically efficient ways to address networks needs | D7.2 | NOA Annual Report | NOA Annual Report Published, part of the Transitional Centralised Strategic Network plan | Q4 2023-24 | On track |  | The NOA will be published as part of the TCSNP2 report this year following the approval to further delay the January 2023 publication to up to (December 2023 and then again until) March 2024. This is to allow for more senior governance activities and extensive stakeholder engagement processes needed ahead of publication. We are currently planning to publish the report at the end of February 2024.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Review LOTI Process with Ofgem and Stakeholders to learn from the first two years of undertaking assessments | Q1 2023-24 | Complete | Q3 2023-24 | We have consulted with Ofgem and the Transmission Owners on how the first two years of LOTI cost-benefit analysis has gone. This yielded an average customer satisfaction score of 7.8 out of 10. Key commentary is summarised below. Positives: - The reports are clearly laid out, well presented and completed on time. Technical concepts, such as Least Worst Regret are well explained and outcomes are accompanied by suitable justification. This allows the TOs to comment in a meaningful way on the ESO report. - The ESO is open on analysis methodologies and approaches ensuring appropriate analysis is done for each study. Likewise the report is flexed to pull out study specific insights. Potential enhancements: - Expand the analysis to include social-economic and carbon benefits [ESO: This has been implemented for CNSP since the LOTI process was introduced] - A simpler exec summary as the technical content, while well explained, is still difficult for all readers to understand. - It is not clear from the report whether the ESO is challenging the TOs input. ESO could add text to the report on any engagement it had with the TOs where assumptions were challenged or changed.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q2 2023-24 | Complete | Q2 2023-24 | We continue to undertake LOTI cost-benefit analysis as and when required.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q3 2023-24 | Complete | Q3 2023-24 | We continue to undertake LOTI cost-benefit analysis as and when required.
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q4 2023-24 | On track
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q1 2024-25 | On track
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q2 2024-25 | On track
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q3 2024-25 | On track
3 | Undertake ad hoc analysis in response to external requests | D7.3 | Large Onshore Transmission Projects (LOTI) (previously Strategic Wider Works (SWW)) projects, Connections and Infrastructure Options Note (CION) and Cost Benefit Analysis (CBA) for small schemes. | Ad-hoc support as required by Ofgem and TOs | Q4 2024-25 | On track
3 | Rollout of Network Services Procurement (formerly Pathfinders) approach and optimise assessment and communication of future needs | D8.1 | Rollout of Network Services Procurement (NPS) approach and optimise assessment and communication of future needs | EC5 tender run | Q3 2023-24 | Delayed - Internal Reasons |  | Enduring tender now expected to take place from April 24 and conclude in August 24, for service to begin in April 25. The delay is due to the review of the service design to ensure we considered the range of possible solutions i.e. DNO connected and offshore assets, to increase competition and achieve best value for consumers. Time from tender completion till service start is for contracted generators to be connected to the tripping scheme by NGET.
3 | Rollout of Network Services Procurement (formerly Pathfinders) approach and optimise assessment and communication of future needs | D8.1 | Rollout of Network Services Procurement (NPS) approach and optimise assessment and communication of future needs | Constraint Management Pathfinder B6 year 3 tender | Q3 2023-24 | Delayed - Internal Reasons |  | We have utilised the one year extension option from the B6 year 2 tender which will ensure that the current service will be in place until September 2026. This is so that we can review the outcome of the ongoing tCSNP studies to determine any future constraint requirements, and focus on regions that will deliver most consumer benefit i.e. regions with high forecast constraint costs.
3 | Rollout of Network Services Procurement (formerly Pathfinders) approach and optimise assessment and communication of future needs | D8.1 | Rollout of Network Services Procurement (NPS) approach and optimise assessment and communication of future needs | Constraint Management Pathfinder B6 year 2 service start date | Q3 2024-25 | On track |  | This service is on schedule to start on time.
3 | Early Competition | D8.4 | Early Competition | Majority of commerical model elements delivered to Ofgem for approval (TRS, PPWCA) | Q1 2023-24 | Complete | Q2 2023-24 | Commercial model submitted to Ofgem.
3 | Early Competition | D8.4 | Early Competition | First generic tender documents and processes delivered to Ofgem to be approved | Q2 2023-24 | Delayed - External Reasons |  | Reviewing timetable with Ofgem as outputs require regulator input
3 | Early Competition | D8.4 | Early Competition | Early Competition contract completed and aligned with relevant licence obligations | Q3 2023-24 | Delayed - External Reasons |  | Reviewing timetable with Ofgem as outputs require regulator input
3 | Early Competition | D8.4 | Early Competition | Implementation complete Project identified for first competition | Q4 2023-24 | Delayed - External Reasons |  | Reviewing timetable with Ofgem as outputs require regulator input
3 | Early Competition | D8.4 | Early Competition | Launch the first Early Competition tender | Q4 2024-25 | Delayed - External Reasons |  | Reviewing timetable with Ofgem as outputs require regulator input. Also dependent on timing of FSO implementation
3 | Refresh and integrate economic assessment tools to support future network modelling needs | D11.1 | Improved identification of when is the most economical time to invest and the most efficient solution | Integration with our network assessment tools | Q3 2023-24 | Complete | Q3 2023-24 | We have refreshed the economic assessment tools that we use to interact with our pan-European market dispatch model. This was done alongside the deployment of our new pan-European market dispatch model. The new model gave us new opportunities to enhance and integrate our tools, for example, by developing them in Python and integrating them with the pan-European dispatch tool via its API.
3 | Refresh and integrate economic assessment tools to support future network modelling needs | D11.1 | Improved identification of when is the most economical time to invest and the most efficient solution | Full integration with Data and analytics platform complete, enabling a joined- up analysis process that allows us to stack different network needs and adjust the level of detail in the analysis, to deliver the most economic decision. | Q4 2024-25 | Delayed - Internal Reasons |  | Based on an initial review of the benefits of this project, we have decided to pause work in this space until we have greater clarity of the functionality of the digital analytics platform and how it may be of use to managing the inputs and outputs for our pan-European market dispatch model. For now, we continue to work using our existing processes to manage the flow of data and are prioritising enhancements to our modelling, such as the inclusion of hydrogen and the use of the capacity expansion module, above this project. This will provide greater consumer benefit and aligns with work on the Central Strategic National Plan (CSNP) and Spatial Strategic Energy Plan (SSEP).
3 | Implement probabilistic modelling | D11.2 | Improved identification of network needs | Developed and implemented digital experience platform. This will provide an interactive platform to allow stakeholders to view network needs and see the impact selected generic options will have on addressing those needs from a technical perspective. | Q4 2023-24 | On track |  | Activity is on track. We have transformed the way we publish our probabilistic results. This year we published our results on the ETYS portal with interactive plots and maps. We are continuously working to improve the way we publish our results and findings to engage our stakeholders more effectively.
3 | Implement probabilistic modelling | D11.2 | Improved identification of network needs | Full integration with Data and analytics platform complete, enabling a joined-up analysis process that allows us to stack different network needs and adjust the level of detail in the analysis, to deliver the most economic decision. | Q4 2024-25 | On track |  | Our in-house tool, POUYA, has gone live and we have started working closely with DAP for the full integration.
3 | Build voltage assessment techniques into an optimisation tool | D11.3 | Improved assessment of voltage requirements, and ability to look across a range of network needs at the same time | Implemented VO tool and identified further enhancements. | Q4 2023-24 | On track |  | We have started an IT project and secured the environment. The team is in place and sprint delivery is ongoing. We have also collected additional user stories to provide enhanced functionalities after going live.
3 | Build voltage assessment techniques into an optimisation tool | D11.3 | Improved assessment of voltage requirements, and ability to look across a range of network needs at the same time | Full integration with Data and analytics platform complete, enabling a joined- up analysis process that allows us to stack different network needs and adjust the level of detail in the analysis, to deliver the most economic decision. | Q4 2024-25 | On track |  | We have started working with the DAP team for the full integration.
3 | Build stability assessment techniques into an optimisation tool | D11.4 | Improved assessment of stability requirements across the network. | Proof of concept for a stability screening tool | Q4 2023-24 | Complete | Q3 2023-24 | We have completed the POC on the stability screening tool.
3 | Build stability assessment techniques into an optimisation tool | D11.4 | Improved assessment of stability requirements across the network. | Implement stability screening tool | Q4 2024-25 | On track |  | We have started development of the solution.
3 | Identify solutions | D12.2 | Potential solutions identified and direction established | Based on the prioritised list of issues, changes are initiated for the high-priority items and potential solutions are developed. | Q1 2023-24 | Complete | Q1 2023-24 | The list of SQSS changes have been reviewed and discussed with relevant stakeholders, new priorities have been established to all the topics.
3 | Identify solutions | D12.2 | Potential solutions identified and direction established | Based on the prioritised list of issues, changes are initiated for the low-priority items and potential solutions are developed. | Q3 2024-25 | On track |  | A few modifications are going, and potential solutions are being identified
3 | Implement changes to the SQSS | D12.3 | Key changes to SQSS made or in progress | Based on the prioritised list of issues, changes are made or in progress for the high-priority items. | Q3 2023-24 | Complete | Q3 2023-24 | A few modifications are going, and potential solutions are being identified
3 | Implement changes to the SQSS | D12.3 | Key changes to SQSS made or in progress | Based on the prioritised list of issues, changes are made or in progress for the low-priority items. | Q4 2024-25 | On track |  | A few modifications are going, and potential solutions are being identified
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Summer Outlook Report Publication of Winter Review & Consultation | Q1 2023-24 | Complete | Q1 2023-24 | 2022 Summer Outlook Report published on 13 April. 2022/23 Winter Review and Consultation published 15 June alongside an early view of winter 2023/24
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of FES suite of documents (including data) | Q2 2023-24 | Complete | Q2 2023-24 | 2023 FES was published on the 10th July.
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Winter Outlook Report | Q3 2023-24 | Complete | Q2 2023-24 | 2023/24 Winter Outlook Report expected to be published on 28 Sep
2 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Summer Outlook Report Publication of Winter Review & Consultation | Q1 2024-25 | Continuous activity |  | 2024 Summer Outlook and 2023/24 Winter Review and Consultation expected to be published in Q1 2024-25 in line with well-established annual processes
3 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of FES suite of documents (including data) | Q2 2024-25 | Continuous activity |  | On track with proposed framework changes
2 | Carry out analysis and scenario modelling on future energy demand and supply | D13.1 | Published Future Energy Scenarios (FES), Winter Outlook and Review, Summer Outlook and other regular external commentary such as blogs from ESO employees on our website. | Publication of Winter Outlook Report | Q3 2024-25 | On track |  | 2024/25 Winter Outlook expected to be published in Q3 2024-25 in line with well-established annual processes
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2 | Update pan-European and country level electricity and energy demand models | Update electricity our supply and demand data for several European countries to reflect the changes within the EU as they continue to evolve their economies to meet net zero decarbonisation. The European countries to model include those that are interconnected to the GB market in addition to a number of additional countries which, whilst further away, still have an impact on the GB market. Data to be benchmarked against the latest Ten Year Network Development Plan from ENTSO and incorporated within our pan-European dispatch model so that the FES, EMR and NOA analysis benefit from it. | Q4 2024-25 | Continuous activity |  | Due in 2025
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2.1 | Provide whole system regional insights | Starting to work with Local Authorities to understand the feedback loop between FES / Distribution scenarios / Local Area Energy Plans. Starting to work with gas networks to agree the granular breakdown of FES scenarios (Natural Gas and Hydrogen) | Q1 2023-24 | Complete | Q1 2023-24 | Work has started to understand the Feedback loop between FES / DFES and Local Area Energy Plans and the granular breakdown of FES scenarios (Natural Gas and Hydrogen) Engagement with the network companies has commenced through the network forum and bilateral discussions. The Call for Evidence for FES 2023 requested stakeholder views on the feedback loop and the regional breakdown of our gas and hydrogen pathways which included engagement with both network companies and local authorities. A project has been kicked off to understand the potential role for the FSO as Regional System Planner. This has included direct engagement with Local Authorities.
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2.1 | Provide whole system regional insights | Whole system regional data and insights provided alongside FES in July Enhanced visualisation launched. Regional data and visualisations added to our Website throughout the year as a appropriate and alongside the annual FES launch User configurable FES view available for Electricity supply and Demand | Q2 2023-24 | Complete | Q2 2023-24 | FES 2023 was launched on July 10th which included regional data and insights. Our visualisation platform was updated alongside the FES and included a user configurable interface for Electricity supply and demand.
3 | Conduct mathematical modelling and market research on local and wider geographic demand information | D13.2.1 | Provide whole system regional insights | Whole system regional data and insights provided alongside FES in July Enhanced visualisation launched. Regional data and visualisations added to our Website throughout the year as a appropriate and alongside the annual FES launch User configurable FES view available for Electricity / Gas / Hydrogen supply and Demand | Q2 2024-25 | On track |  | Due in July 2024
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q1 2023-24 | Complete | Q1 2023-24 | Launch date communicated early with Ofgem and in line with previous years. (At time of writing it is now complete, launched on 10 July as agreed)
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES suite of documents (including data) | Q2 2023-24 | Complete | Q1 2023-24 | On track
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q3 2023-24 | Complete | Q3 2023-24 | On track and forms part of our ongoing engagement plan Published additional changes document in September
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q4 2023-24 | On track |  | On track and forms part of our ongoing engagement plan. Recently held stakeholder events for input in to framework design and analysis inputs. Ongoing communication via newsletters and bilateral meetings.
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q1 2024-25 | On track |  | On track and forms part of our ongoing engagement plan
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES suite of documents (including data) | Q2 2024-25 | On track |  | On track
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q3 2024-25 | On track |  | On track and will form part of our engagement plan for the year
3 | Maintain external communication channels with consumers and stakeholders | D13.3 | Shared insights on future energy expectations and requirements | Publication of FES-related insights via website and FES / ESO Newsletter | Q4 2024-25 | On track |  | On track and will form part of our engagement plan for the year
3 | FES: Bridging the gap to net zero | D13.4 | Bridging the Gap - produce evidence-based recommendations to support development of net zero policy | Delivery of a stakeholder informed report with recommendations for near term actions for net zero. | Q4 2023-24 | On track | Q1 2023-24 | Focussing on enablers and dependencies for accelerating heat decarbonisation - workshops throughout September and October
3 | FES: Bridging the gap to net zero | D13.4 | Bridging the Gap - produce evidence-based recommendations to support development of net zero policy | Delivery of a stakeholder informed report with recommendations for near term actions for net zero. | Q4 2024-25 | On track | Q1 2024-25 | Annual piece of work so not commenced yet but will commence in Q1 2024. Link to Advisory role for future FSO
2 | FES: Integrating with other networks and supporting DNOs to develop their own DFES processes | D13.5.3 | Enhance our energy modelling to reflect stakeholder feedback and changes to the credible pathways to net zero | Development plan in place | Q4 2023-24 | On track |  | Our energy modelling has been updated for FES24 to enhance our ability to reflect H2 supply locations. We are continuing to work through the modelling requirements to support CSNP with internal and external stakeholders.
3 | Provide contractual expertise and management of connection contracts including provision of connection offers to customers | D14.1.1 | Managing an increasing volume of connection offers for customers | Ongoing activity – success measured by positive customer feedback on our service | Q4 2024-25 | On track |  | Ongoing activity
3 | Provide contractual expertise and management of connection contracts including provision of connection offers to customers | D14.1.2 | Contract management of connection agreements | Ongoing activity – success measured by positive customer feedback on our service | Q4 2024-25 | On track |  | Ongoing activity
3 | Ensure Grid Code compliance of new connections | D14.2.1 | Compliance monitoring of new connections in accordance with Grid Code provisions | Ongoing activity – success measured by positive customer feedback on our service | Q4 2024-25 | On track |  | Ongoing activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Run a new type of meeting as part of Connections process with DNOs and TOs focused on review of new connections still being processed by DNOs and suitability of DER as an option [at this point DER as a solution needs to be understood by all] | Q1 2023-24 | Complete | Q3 2023-24 | The ESO team is working seamlessly with the DNO community to push solutions forward for generation and demand sites that want to connect at a lower voltage level. We have a dedicated Demand team which has a sepcific account manager for each DNO, who is there to support in providing solutions to DER customers, in tandem with the relevant DNO. We have also increased resource to facilitate the work through the ENA led Strategic Connection Group, to help deliver greater capacity at a DNO level by assessing 'Technical limits' across the T/D interface. This is providing material benefit for DER applicants.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously delivery on the use of DER, learn lessons and implement improvements | Q2 2024-25 | On track |  | On Track
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Request feedback from Customers and DNOs | Q3 2023-24 | Complete | Q3 2023-24 | This has been done in tandem with DNO colleagues through the SCG work. Furthermore, we run monthly webinars with the industry, which offers an opportunity to discuss their experiences and questions around our activities in the Connection space. We also look to host twice yearly, customer seminars - which brings the wider industry together.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously delivery on the use of DER, learn lessons and implement improvements | Q4 2024-25 | Complete | Q3 2023-24 | Complete
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously deliver on the use of DER, learn lessons and implement improvements | Q1 2024-25 | Complete | Q3 2023-24 | Complete
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.1 | Establish dedicated Distributed Energy Resource (DER) account management function | Continuously delivery on the use of DER, learn lessons and implement improvements | Q3 2024-25 | Complete | Q3 2023-24 | Complete
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q1 2023-24 | Complete | Q1 2023-24 | Complete
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q2 2023-24 | Complete | Q2 2023-24 | Complete
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q3 2023-24 | Complete | Q3 2023-24 | Complete
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q4 2023-24 | On track |  | On Track
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q1 2024-25 | On track |  | On Track
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q2 2024-25 | On track |  | On Track
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q3 2024-25 | On track |  | On Track
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.3 | Whole electricity system connection seminars on an ongoing basis | Ongoing seminars | Q4 2024-25 | On track |  | On Track
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Submit IT investment paper through internal governance process and obtain approval of scope and expenditure Engage with customers on ways to improve connections journey and ways of enhancing the portal | Q1 2023-24 | Complete | Q1 2023-24 | Future releases of the Connections portal are planned and the functionality backlog has been agreed. Sessions with industry stakeholders are ongoing with some smaller targeted sessions with specific groups of stakeholders already held and larger stakeholder events planned for the end of July 2023.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Further develop concept of new register, platform and connection with other systems [salesforce and customer portal]; Liaise with relevant internal stakeholders to verify concept and requirements | Q2 2023-24 | Complete | Q2 2023-24 | The functionality for the Connections portal is constantly being developed, with more functionality being added every 2-3 months throughout the BP2 period. The functionality being added is underpinned by stakeholder feedback.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Further development and testing - engage with relevant focus groups | Q3 2023-24 | Complete | Q3 2023-24 | This is an ongoing activity. We are currently carrying out feature development sessions with industry parties such as; consultants, DNOs and TOs to enhance portal functionality.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Implementation of updates to ESO Portal | Q4 2023-24 | On track |  | Continuous Activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Obtain feedback on the new platform from internal and external stakeholders | Q1 2024-25 | On track |  | Stakeholder feedback sessions planned for July 2023 and functionality being introduced directly into the portal to obtain customer feedback.
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Continuous review, maintenance and updates to the platform | Q2 2024-25 | On track |  | Ongoing Activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Continuous review, maintenance and updates to the platform | Q3 2024-25 | On track |  | Ongoing Activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.4 | Improving Systems and Data | Continuous review, maintenance and updates to the platform | Q4 2024-25 | On track |  | Ongoing Activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.5 | Improving our internal processes | Improved customer feedback indicating customers welcome changes to connections processes | Q4 2024-25 | Continuous activity |  | Ongoing Activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.6 | Proposing future policy and code improvements | ESO has identified helpful policy and code changes, including ENA guidance and new ESO policies, which are supported by relevant stakeholders. Industry code modifications proposed. | Q4 2023-24 | Continuous activity |  | Ongoing Activity
3 | Further enhance the customer connection experience, including broader support for smaller parties | D14.3.6 | Proposing future policy and code improvements | ESO has identified helpful policy and code changes, including ENA guidance and new ESO policies, which are supported by relevant stakeholders. Industry code modifications proposed. | Q4 2024-25 | Continuous activity |  | Ongoing Activity
3 | Facilitate development of the customer connections portal | D14.4.1 | Implement first phase of the ESO connections portal, including online account management and integration with other network organisation websites | Deliver changes based on customer feedback | Q1 2023-24 | Complete | Q1 2023-24 | Two further releases have been implemented since the launch of MVP in March 2023 including new functionality for calculation of application fees as well as other front end and back end enhancements.
3 | Facilitate development of the customer connections portal | D14.4.1 | Implement first phase of the ESO connections portal, including online account management and integration with other network organisation websites | Deliver changes based on customer feedback | Q2 2023-24 | Complete | Q2 2023-24 | Complete
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Submit revised IT investment paper through internal governance process and obtain approval of scope and expenditure | Q1 2023-24 | Complete | Q1 2023-24 | IT investment paper submitted
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Further develop concept of phase 2 deliverables and identify different stages of deliverables along with key stakeholders to work with | Q2 2023-24 | Complete | Q2 2023-24 | Future releases of the Connections portal are planned and the functionality backlog has been agreed. Sessions with industry stakeholders are ongoing with some smaller targeted sessions with specific groups of stakeholders already held and larger stakeholder events planned for the end of July 2023.
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Development of concept designs | Q3 2023-24 | Complete | Q3 2023-24 | Ongoing activity
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Development of concept designs | Q4 2023-24 | On track |  | Ongoing activity
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Review and UAT for scheduled deliverables in Q3 & Q4 | Q1 2024-25 | On track |  | Ongoing activity
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Continuous development of further elements for later delivery | Q2 2024-25 | On track |  | Ongoing activity
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Delivery of elements of the phase 2; Continuous development of further elements for later delivery | Q3 2024-25 | On track |  | Ongoing activity
3 | Facilitate development of the customer connections portal | D14.4.2 | Phase 2 of the connections portal concluded | Delivery of elements of the phase 2; Continuous development of further elements for later delivery | Q4 2024-25 | On track |  | Ongoing activity
3 | Connections Reform | D14.5.1 | Connections Reform Phase 1 | Final iteration of problem statement and proposal paper to Ofgem to address concerns and deficiencies of current codified connections process to support Phase 2 Produce a connections reform roadmap | Q1 2023-24 | Complete | Q1 2023-24 | Complete
3 | Connections Reform | D14.5.1 | Connections Reform Phase 1 | Deliver TEC Amnesty and Queue Management Process, CPA review and modelling of storage review | Q2 2023-24 | Delayed - External Reasons |  | TEC amnesty: 4.1 GW of TEC reductions and terminations are being implemented. Ofgem approved CMP376 for queue management including WACM7 (applying to existing queue with connection dates after 27Nov2025) and we have published the notice to industry, giving customers 6months to respond before milestones are applied to their connection agreement. CPA review and modelling of storage: CPA and TRW delivery continues in England and Wales. The methodology has been agreed in Scotland and CPAs are being delivered. We have rescheduled the completion date for issuing accelerated connection offers as a result of the CPA review to August 2024. This delay allows the inclusion of distribution customers as well as directly connected transmission customers, implementing a capacity reallocation approach and it will also allow the 2nd-step offers from the 2-step process in England & Wales to be prioritised for deliver by the deadline of 29 February 2024.
3 | Connections Reform | D14.5.2 | Connections Reform Phase 2 | Start the connections reform Phase 2 as per roadmap - workgroups stage for definition of the problem and what good looks like | Q1 2023-24 | Complete | Q1 2023-24 | Reform project brought forward with phase 2 initiated during BP1. Revised milestones proposed for approval to reflect schedule published in June 2023 consultation.
3 | Connections Reform | D14.5.2 | Connections Reform Phase 2 | Continue to enable workgroups for discussion and definition of the problems; Touchpoints with ERSG, OFGEM, BEIS and wider stakeholder group | Q2 2023-24 | Complete | Q2 2023-24 | Reform project brought forward with this activity delivered before the connections reform consultation was published in June 2023. Revised milestones proposed for approval to reflect schedule published in June 2023 consultation.
3 | Connections Reform | D14.5.2 | Connections Reform Phase 2 | Complete Phase 2 - obtain a clear mapping of the problems to be addressed as part of the reform, focus areas for Phase 3 and summary of what good looks like | Q3 2023-24 | Complete | Q3 2023-24 | Phase 2 final recommendations for connections reform published December 2023 and launch events held, completing phase 2.
3 | Connections Reform | D14.5.3 | Connections Reform Phase 3 | Produce intial implementation programme and scope for review as part of project and ESO governance process, plus presentation to OFGEM and BEIS; look to share with wider industry. Decision point on whether to progress with current set of solutions or if something different needs to be done (with impact to the programme to be considered) Code and regulation changes framework to enable all relevant changes ahead of implementation. | Q1 2024-25 | On track |  | Reform project brought forward. Final recommendations for connections reform published December 2023, including implementation plan for Phase 3 and 4. The Connections Reform Steering Group and Delivery Partners Executive Group contributed to the final recommendations and supported their publication. The final recommendations propose adopting an urgent code modification process in 2024 to enable go-live of the reformed connections process in January 2025. A new Connections Process Advisory Group and a Connections Delivery Board have been established to guide and oversee delivery throughout 2024.
3 | Connections Reform | D14.5.3 | Connections Reform Phase 3 | New process(es) are defined and agreed on by all relevant and impacted organisations Implementation programme with relevant roles and responsibilities to be reviewed and agreed upon by all relevant stakeholders and organisations | Q2 2024-25 | On track |  | Reform project brought forward. Final recommendations for Connection Reform published December 2023. Phase 3 is underway and a Connections Process Advisory Group has been established to oversee detailed design and development of code modification proposals in early 2024.
3 | Connections Reform | D14.5.3 | Connections Reform Phase 3 | Initiate phase 3 of the reform by establishing the various working groups to enable design and development of the various solutions and strategies to address the changes required | Q3 2023-24 | Complete | Q3 2023-24 | Reform project brought forward. Final recommendations for Connection Reform published December2023. Phase 3 is underway and a Connections Process Advisory Group has been established to oversee detailed design and development of code modification proposals in early 2024.
3 | Connections Reform | D14.5.3 | Connections Reform Phase 3 | Continue to enable workgroups for discussion and definition of the problems; Touchpoints with ERSG, OFGEM, BEIS and wider stakeholder group | Q4 2023-24 | On track |  | Reform project brought forward. Final recommendations for connections reform published December 2023, following extensive engagement with stakeholders through design work groups, webinars, steering group and Delivery Partners Executive Group including Ofgem, DESNZ and wider stakeholders. Connections Process Advisory Group and Connections Delivery Board established for delivery throughout 2024.These milestones need review following publication of the government Connections Action Plan; these original BP2 milestones do not reflect the scale and intensity of connections change delivery.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 4 | Initiate implementation programme | Q3 2024-25 | On track |  | Reform project brought forward. Final recommendations for connections reform published December 2023, including the implementation plan for the detailed design and implementation of the reforms. These milestones need review following publication of the government Connections Action Plan; these original BP2 milestones do not reflect the scale and intensity of connections change delivery.
3 | Connections Reform | D14.5.4 | Connections Reform Phase 4 | Review and update of programme, along with report on findings from review and requirement to work on any of the proposed changes to be further developed during the implementation phase that is proposed to last up to 24 months | Q4 2024-25 | On track |  | Reform project brought forward. Final recommendations for connections reform published December 2023, including the implementation plan for the detailed design and implementation of the reforms by January 2025. These milestones need review following publication of the government Connections Action Plan; these original BP2 milestones do not reflect the scale and intensity of connections change delivery.
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q1 2023-24 | Complete | Q1 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation and Grid Forming are ongoing, it will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q2 2023-24 | Complete | Q2 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, it will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q3 2023-24 | Complete | Q3 2023-24 | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q4 2023-24 | On track |  | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q1 2024-25 | On track |  | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q2 2024-25 | On track |  | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q3 2024-25 | On track |  | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.1 | System Operability Framework (SOF) documentation to identify and quantify operability needs in short and long-term planning timescales, encouraging the development of market-based solutions wherever possible | Deliver System Operability publications in response to real time system challenges or other future system developments. Topics are under development with wider industry stakeholders including key operability issues to reach zero carbon system operation ambition and what’s next including whole energy system issues. Undertake improvements to identify topics and deliver publication in accordance with stakeholder feedback and/or the ESO review | Q4 2024-25 | On track |  | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.2 | Innovation projects developing new operability solutions – undertake innovation projects, as appropriate, to test operability solutions | Identify and initiate new innovation project | Q4 2023-24 | On track |  | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Develop the System Operability Framework (SOF) and provide solutions up to real time of network related operability issues | D15.1.2 | Innovation projects developing new operability solutions – undertake innovation projects, as appropriate, to test operability solutions | New innovation project delivered and learning has been captured in developing of SOF | Q4 2024-25 | On track |  | System strength webinar was held in April to gather the views from the wider industry, the NIA projects on system Strength, oscillation identification, enhanced RMS model and Grid Forming are ongoing, D3 project was successfully delivered and the new impedance scan tool is being tested for SSO analysis. All the learnings will help us to further develop our understanding in those areas and formulate the policy change or market based solutions
3 | Provide technical support to the connections process | D15.2.1 | Updates to customer offers and agreements – provide technical support to the connection offer process (as set out in activity A14.1) and assess offers to determine future operability need | As required and provide technical support to delivery of the connections hub in activity group A14 | Q4 2024-25 | Continuous activity |  | Once the policy changes have been approved, they are reflected into the connection offers and agreements
3 | Provide technical support to the connections process | D15.2.1 | Updates to customer offers and agreements – provide technical support to the connection offer process (as set out in activity A14.1) and assess offers to determine future operability need | As required and provide technical support to delivery of the connections hub in activity group A14 | Q4 2024-25 | Continuous activity |  | Once the policy changes have been approved, they are reflected into the connection offers and agreements
3 | Assess the technical implications of framework developments and implement changes into business procedures and systems | D15.3.1 | Changes to business procedures and processes following framework developments – provide technical expertise to development of Codes and Standards and assess impact of change to operability processes. | Provide ongoing technical support to modifications as required (including those raised through open governance) – the level of resource required can vary hugely from one to another | Q4 2024-25 | Continuous activity |  | Once the policy and framework changes have been approved, they are reflected into the business procedures and process
3 | Assess the technical implications of framework developments and implement changes into business procedures and systems | D15.3.1 | Changes to business procedures and processes following framework developments – provide technical expertise to development of Codes and Standards and assess impact of change to operability processes. | Provide ongoing technical support to modifications as required (including those raised through open governance) – the level of resource required can vary hugely from one to another | Q4 2024-25 | Continuous activity |  | Once the policy and framework changes have been approved, they are reflected into the business procedures and process
3 | Manage our operational data and modelling requirements | D15.4.1 | Data transfers between network organisations in accordance with current Grid Code and STC requirements – managing operational data flows across network companies to underpin offline network analysis in the ESO. | Delivery ETYS and NOA models | Q3 2023-24 | Complete | Q3 2023-24 | All 2023 ETYS Winter models completed (Years 1, 2, 4, 7, 9, 12) and released by 1st September 2023. Summer minimum Year 1 model released on 15/09/2023.
3 | Manage our operational data and modelling requirements | D15.4.1 | Data transfers between network organisations in accordance with current Grid Code and STC requirements – managing operational data flows across network companies to underpin offline network analysis in the ESO. | Delivery ETYS and NOA models | Q3 2024-25 | On track |  | Prepare for new requirements needed in 2024 ETYS Model
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q1 2023-24 | Complete | Q1 2023-24 | engaging and co-ordinating with network owners is a key continuous activity
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q2 2023-24 | Complete | Q2 2023-24 | engaging and co-ordinating with network owners is a key continuous activity
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q3 2023-24 | Complete | Q3 2023-24 | engaging and co-ordinating with network owners is a key continuous activity
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q4 2023-24 | Continuous activity |  | engaging and co-ordinating with network owners is a key continuous activity
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q1 2024-25 | Continuous activity |  | engaging and co-ordinating with network owners is a key continuous activity
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q2 2024-25 | Continuous activity |  | engaging and co-ordinating with network owners is a key continuous activity
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q3 2024-25 | Continuous activity |  | engaging and co-ordinating with network owners is a key continuous activity
3 | Manage our operational data and modelling requirements | D15.4.2 | Technical modelling for use across the ESO – ongoing development and support of system data and models used to analyse future network needs and operability solutions by different teams in the ESO. | As required by Grid Code and STC obligations | Q4 2024-25 | Continuous activity |  | engaging and co-ordinating with network owners is a key continuous activity
3 | Manage our operational data and modelling requirements | D15.4.3 | Automation of data exchange mechanism and preparation for CIM implementation | Identify initiative which will automate the data exchange mechanism Commence preparation for data exchange enhancements with network organisations | Q4 2023-24 | On track |  | This is a Q4 2023-24 deliverable that it reliant on GC139 being agreed in D15.6.2 by Q3 2023-24
3 | Manage our operational data and modelling requirements | D15.4.3 | Automation of data exchange mechanism and preparation for CIM implementation | Implementation of data exchange automation Prepared for data exchange enhancements with network organisations | Q4 2024-25 | On track |  | This is a Q4 2024-25 deliverable
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Testing and commissioning of first GEMS pilot boundaries | Q1 2023-24 | Delayed - External Reasons |  | During the detail design phase, some challenges were identified by SPT to deliver the GEMS solution as described in the ESO Technical Specification. It was decided to pause current ESO IT development work, whilst SPT and ESO work through to find a way forward to deliver the functionalities. A proposal to mover forward is submitted to SPT and it is under review by them.
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Design and integration of GEMS functionality with SPD ANM scheme. | Q2 2024-25 | On track |  | SPT are facing challenges with design and delivery of GEMS. SPT and ESO are working on options to move forward. ESO are working with SPD to mitigate the challenges.
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Expansion of functionality to further boundaries on a system needs basis. | Q4 2023-24 | Delayed - External Reasons |  | During the detail design phase, some challenges were identified by SPT to deliver the GEMS solution as described in the ESO Technical Specification. It was decided to pause current ESO IT development work, whilst SPT and ESO work through to find a way forward to deliver the functionalities. A proposal to mover forward is submitted to SPT and it is under review by them.
3 | Develop Regional Development Programmes (RDPs) | D15.11.2 | Forward Plan 2020-21 RDP - Generation Export Management Scheme (GEMS) | Commissioning of first DER onto combined GEMS and SPD ANM functionality. | Q4 2024-25 | On track |  | SPT are facing challenges with design and delivery of GEMS. SPT and ESO are working on options to move forward. ESO are working with SPD to mitigate the challenges.
3 | Develop Regional Development Programmes (RDPs) | D15.5.2 | RDP2 of RIIO-2 (MW dispatch, South East, UKPN) | IT implementation phase complete | Q2 2023-24 | Delayed - External Reasons |  | ESO Registration functionality releases complete to facilitate DER registrations. Joint Integration Testing progressing and targeting a March 2024 technical go live across both ESO and DNO systems.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Working with the DNO, continue to undertake IT requirements and design for new operability functionality | Q1 2023-24 | Delayed - External Reasons |  | RDP3 is intended to be the vehicle to deliver the post MVP requirements and enhancements to our RDP1 (MWD service in the NGED DNO area). RDP1 delivery timescales were significantly impacted by the need to deliver a bespoke private Web service link for data exchanges to meet the NGED security protocols, having a resultant knock on effect to the delivery timescales of this RDP. The RDP1 infrastructure is now in place allowing us to progress with the post MVP enhancements as intended - internal ESO assessment and prioritisation of the existing Product Backlog has been completed with DNO requirements gathering and design commencing in January.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Complete IT requirements and design | Q2 2023-24 | Delayed - External Reasons |  | RDP3 is intended to be the vehicle to deliver the post MVP requirements and enhancements to our RDP1 (MWD service in the NGED DNO area). RDP1 delivery timescales were significantly impacted by the need to deliver a bespoke private Web service link for data exchanges to meet the NGED security protocols, having a resultant knock on effect to the delivery timescales of this RDP. The RDP1 infrastructure is now in place allowing us to progress with the post MVP enhancements as intended - internal ESO assessment and prioritisation of the existing Product Backlog has been completed with DNO requirements gathering and design commencing in January.
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Complete enhancements to new service and final implementation | Q4 2024-25 | On track |  | On track
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Complete IT development and testing; ongoing implementation of solution | Q1 2024-25 | On track |  | On track
3 | Develop Regional Development Programmes (RDPs) | D15.5.3 | RDP3 of RIIO-2 (wider rollout & enhancements, WPD) | Assess enhancements to new service in accordance with operability needs and customer feedback | Q2 2024-25 | On track |  | On track
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Working with the DNO, continue to undertake IT requirements and design for new operability functionality | Q1 2023-24 | Delayed - External Reasons |  | RDP2 (UKPN MWD MVP) has been delayed from BP1 due to delay in agreeing MVP scope with DNO and is now due for go live in early 2024 - this project is dependent on completion of that phase. Internal ESO review of existing Product Backlog items has taken place and DNO session planned in January to undertake IT requirements gathering and new functionality design.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Complete IT requirements and design | Q2 2023-24 | Delayed - External Reasons |  | RDP2 (UKPN MWD MVP) has been delayed from BP1 due to delay in agreeing MVP scope with DNO and is now due for go live in early 2024 - this project is dependent on completion of that phase. Internal ESO review of existing Product Backlog items has taken place and DNO session planned in January to undertake IT requirements gathering and new functionality design.
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Complete enhancements to new service and final implementation | Q4 2024-25 | On track |  | On track
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Complete IT development and testing; ongoing implementation of solution | Q1 2024-25 | On track |  | On track
3 | Develop Regional Development Programmes (RDPs) | D15.5.4 | RDP4 of RIIO-2 (wider roll out & enhancements UKPN) | Assess enhancements to new service in accordance with operability needs and customer feedback | Q2 2024-25 | On track |  | On track
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Establish enduring process to determine needs at GSPs | Q2 2023-24 | Complete | Q2 2023-24 | Factoring in our ongoing work through the ESO's Five Point Plan to Accelerate Connections, we have now drafted a process to determine a needs case at each GSP. This is currently undergoing final internal approval prior to being shared with stakeholders for review and feedback.
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Rollout process and seek feedback from stakeholders | Q4 2023-24 | On track |  | Following publication of the process, we will work with stakeholders to review and implement feedback, ahead of trialling at initial GSPs.
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Test application of process at one or more sites | Q2 2024-25 | On track |  | We are working with SSEN to trial the process at their Abernethy network.
3 | Develop Regional Development Programmes (RDPs) | D15.5.5 | Deliver GB rollout of functionality developed through initial RDPs | Implement enduring ongoing process (BAU) | Q4 2024-25 | On track |  | Following successful tests at the nominated sites, BAU processes will be updated to reflect the relevant changes.
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Go / No go decision to progress RDP implementation; If yes, commence detailed RDP development | Q1 2023-24 | Complete | Q1 2023-24 | We have identified a number of opportunities where RDP5 can support the roll-out of functionality necessary to support the ESO's Five Point Plan to accelerate connections.
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Complete IT requirements and design | Q2 2024-25 | On track |  | On track
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Complete detailed RDP development ahead of IT build. | Q3 2023-24 | Delayed - Internal Reasons |  | Following on the outcome of GSP technical limits at Strategic Connections Group work, the RDP5 is developing detailed requirements to enable GSP technical limits with all England and Wales DNOs.
3 | Develop Regional Development Programmes (RDPs) | D15.5.6 | RDP5 of RIIO-2 | Commence IT implementation in order to test new service solution. | Q4 2024-25 | On track |  | On track
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Go / No go decision to progress RDP implementation; If yes, commence detailed RDP development | Q1 2023-24 | Complete | Q1 2023-24 | We have identified a number of opportunities where RDP6 can support the roll-out of functionality necessary to support the ESO's Five Point Plan to accelerate connections.
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Complete IT requirements and design | Q2 2024-25 | On track |  | On Track
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Complete detailed RDP development ahead of IT build. | Q3 2023-24 | Delayed - Internal Reasons |  | Depend on the outcome of GEMS programme, ESO and SPD possibly be able deliver a transmission constraint management service for DERs via RDP6.
3 | Develop Regional Development Programmes (RDPs) | D15.5.7 | RDP6 of RIIO-2 | Commence IT implementation in order to test new service solution. | Q4 2024-25 | On track |  | On track
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q1 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q2 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q3 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Grid Code mods progressed or submitted for approval | Q4 2023-24 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.2 | Further Grid Code modification implementation (arising, for example, from O/N 2020 work programme, discussions with industry participants and/or in response to Ofgem’s Call For Evidence on Distributed Generation visibility) | Provide ongoing technical support and input to the code development process | Q4 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. | Further upgrade to offline modelling tool software / service pack | Q2 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.6 | Deliver major upgrades to our offline modelling tools, which will allow us to model a more complex system. | Integration of offline modelling tools with Data and Analytics Platform | Q4 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.7 | Deeper Outage Planning go live in Offline Network Modelling | Feed findings from deliverable A16.3.2 and any Grid Code modifications into future modelling scoping and development | Q4 2023-24 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.7 | Deeper Outage Planning go live in Offline Network Modelling | Feed findings from deeper access work into offline network modelling development | Q4 2024-25 | On track |  | On track for delivery
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | Learning from NIA projects (such as TOTEM) to define the requirements for EMT modelling work | Q1 2023-24 | Complete | Q1 2023-24 | NIA project TOTEM led by SSEN, provided base case EMT network component model based on ETYS 2021 Year 1. This will be used as base model for ESO to develop GB wide EMT model. The learnings such as dispatch tool requirement to analyse multiple scenarios, computational performance required will be taken forward to build future model building activities. DETECTS is another innovation project, where the SE Coast model with Users model integrated has been obtained. The main learning is on the integration of Users model to wider EMT model. More innovation projects, such as developing tools to analyse the system, are ongoing. Based on these learnings, ESO in discussion with wider industry, to build and maintain the GB wide EMT model for future.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | Engage with wider industry and produce a roadmap to develop and maintain EMT models | Q2 2023-24 | Complete | Q2 2023-24 | ESO engaged with all onshore TOs through innovation project such as TOTEM to develop the base case GB wide EMT model. ESO is currently working with SSEN-T on EMT analysis. ESO is working in partnership with NGET on development of co-simulation NIA project. The JPC approved to form JPCMG subgroup on EMT modelling. ESO also having continuous engagement with wider industry (AEMO, G_PST, NERC, ESIG group) on learning and developing GB wide EMT model.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | Identify the data requirements and develop process to collect required data and build initial EMT model. | Q4 2023-24 | On track |  | Learnings from all NIA innovation projects are being used by ESO to define these requirements. ESO also engaged with wider industry (AEMO, NERC EMTTF, ESIG) in the world and their learnings also being used to develop these requirements.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | To carry out initial EMT simulations for the GB network | Q1 2024-25 | Complete | Q1 2023-24 | ESO have already started to carry out EMT simulations for single plants/ HVDC. ESO obtain the initial model from DETECTS innovation project and started the regional analysis on GB.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | To define the requirements for full GB system EMT simulation using learning from NIA projects (co-simulation analysis innovation project in D15.6.9) | Q2 2024-25 | On track |  | After completing the feasibility of co-simulation analysis (between PowerFActory and PSCAD) through innovation projects, requirements will be defined.
3 | Transform our capability in modelling and data management | D15.6.8 | Development & ongoing maintenance of EMT Capabilities | To carry out EMT simulations to analyse control interactions, system oscillations and power quality studies. Developed plan for ongoing maintenance of EMT model(s). | Q4 2024-25 | On track |  | ESO started to carry out EMT simulations for single plants/ HVDC. ESO obtain the initial model from DETECTS innovation project and developing the analysis skills. Different system analysis with wider GB model, obtained from TOTEM project, will be carried out.
3 | Transform our capability in modelling and data management | D15.6.9 | Co-simulation analysis innovation project | Engage with wider industry (different TOs) to start the potential innovation project for co-simulation works. | Q1 2023-24 | Complete | Q1 2023-24 | Engaged with NGET TO on requirements of co-simulation (between PowerFactory and PSCAD model). ESO is working with NGET to set up a new NIA project called Co-Simulation. Co-simulation NIA project is expected to start in 2 weeks. ESO also engaging with OPAL-RT and other academia on possible NIA projects as well.
3 | Transform our capability in modelling and data management | D15.6.9 | Co-simulation analysis innovation project | Evaluate the feasibility of co-simulation modelling between OLTA (PowerFactory) and PSCAD. | Q4 2023-24 | On track |  | With the NIA project on co-simulation, working with NGET, ESO will evaluate the feasibility of co-simulation between PowerFactory and PSCAD. ESO also will explore on other opportunities.
3 | Deliver enhanced frequency control by 2025 | D15.7.1 | Commence System State Targeted Monitoring and Control System (MCS) first stage roll out. | Phase 1 (non-operational demonstration) implemented | Q3 2023-24 | Delayed - External Reasons |  | Due to the long delay in getting contract signed between parties, the completion of non-operational demonstration date is expected to go beyond the current scheduled date. Currently change Request has been submitted and the expected completion of this milestone is Q2 2024-25. Through CMF process the revised milestone date has been updated. t is expected to be completed within BP2 period. With the Statement of Work has been agreed with GE Digital, the confidence level of completing this milestone is increased to HIGH.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Support ESO initiatives to remove technical barriers to ensure whole electricity system coordination & distributed flexibility market participation. | Q4 2023-24 | On track |  | Actively engaged with Open Networks and DNO's. Co-leading a number of workstreams to facilitate Flex Market delivery including policy/code changes.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement on DSO transition to support ongoing developments and transition policy into the relevant codes and frameworks. | Q4 2023-24 | On track |  | Actively engaged with Open Networks and DNO's. Co-leading a number of workstreams to facilitate Flex Market delivery including policy/code changes. Linked also to Market Facilitation discussions as well as this role will hold the pen on the standard ways of working. this will then drive forward Open Networks
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement in the Open Networks project to support ongoing developments and lead Work Stream 4 Whole Energy Systems | Q4 2023-24 | On track |  | Actively engaged on workstreams on Open Networks, Currently co-leading on several to drive forward change and increase pace of change. we have a proposed way forward on Primacy rules and continue to engage with all stakeholders.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Support ESO initiatives to remove technical barriers to ensure whole electricity system coordination & distributed flexibility market participation. | Q4 2024-25 | On track |  | Engaging on Strategic Connections Group and other forums to ensure that coordination across networks drives the right changes in the industry. Working across the business to ensure that ESO is wholly cognizant of change and represented to ensure best outcomes for customers and facilitate a flexible energy system
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement on DSO transition to support ongoing developments and transition policy into the relevant codes and frameworks . | Q4 2024-25 | On track |  | Actively engaged with industry to ensure that all codes and agreements can reflect the changing nature of the system. Objective needs refinement as it mirrors another objective.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.1 | Develop policy areas to accelerate whole electricity flexibility | Undertake active engagement in the Open Networks project to support ongoing developments and lead Work Stream 4 Whole Energy Systems | Q4 2024-25 | On track |  | We are engaged on Open Networks and making positive contributions to achieving the outcomes needed.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Initiate project scoping with external stakeholders to enable operational visibility of DER | Q1 2023-24 | Complete | Q1 2023-24 | We have initiated Project scoping with internal stakeholders to identify DER visibility use cases. Identified relevant external stakeholders. Next step to engage externally to produce a high level view of External stakeholders expectations.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Complete project scoping with external stakeholders to enable operational visibility of DER | Q2 2023-24 | Complete | Q3 2023-24 | We have completed work to produce a DER Visibility Roadmap strategy. We undertook a cross functional view to produce detailed user requirements across ESO & external stakeholders as well considering regulatory, data and technology architecture aspects needed to deliver DER visibility. This holistic approach is expected to reduce risk & maximise consumer benefit.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Initiate IT discovery phase to understand impacts on required changes to systems and define change strategy | Q3 2023-24 | Delayed - Internal Reasons |  | DER Visibility roadmap strategy has defined vision, strategy, use cases, data points and roadmap for delivery. This included a high level technology capability assessment. The outputs of this activity have been shared throughout with the IT / DD&T discovery team who will produce a mandate for the IT /DD&T Discovery activity, to be approved mid January 2024 Mobilisation of the IT / DD&T Discovery team will occur mid January 2024. This manifests as a two week delay against the milestone.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Complete IT discovery phase and identify costs of implementation | Q4 2023-24 | On track |  | Despite two week delay to start of discovery kick off, there is some optimism to bring back on track and deliver faster due to the in depth work carried out to date as part of the DER visibility roadmap strategy. This will be confirmed once IT discovery team mobilise in early January, hence low delivery confidence at this stage.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Commencement of requirements and design phase to develop detailed IT solution to enable DER visibility | Q1 2024-25 | On track |  | Commencement of requirements and design phase for IT solution(s) will follow on from completion of IT/DD&T Discovery, expected to start in May 24.
3 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.2 | Enabling whole electricity flexibility service provision through operational visibility | Commence building the storage and transfer capability to utilise bigger volumes of data associated with a larger number of operational metering data points | Q4 2024-25 | On track |  | Specific IT solution(s) will be identified in the discovery phase and designed in the design phase. These details will scope how this milestone will be met.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Initiate IT discovery phase for primacy implementation to understand impacts on required changes to systems and define change strategy | Q1 2023-24 | Delayed - External Reasons |  | Delayed due to lack of clarity around Primacy rules, Open Networks and Market Facilitation. We continue to work with the DNO's to implement ways of working but alot depends on enabling works. We now have a way forward and the work around discovery has started.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Complete IT discovery phase and identify costs of implementation | Q2 2023-24 | Delayed - External Reasons |  | Dependency on completion of discovery phase which can't be started until we have more clarity on the Primacy rules planning which is in part dependent on DNO's and Market Facilitation consultation. Discovery has started and we have a proposed way forward.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Commencement of requirements and design phase to implement primacy rules into operational IT systems | Q3 2023-24 | Delayed - External Reasons |  | Dependent on outputs of Discovery which is delayed in part due to lack of direction around Open Networks but we are exploring sensible new ways of enabling primacy rules. Delayed but we are now on Discovery phase work and working through our ESO plans.
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Continue to lead on Open Networks work to deliver primacy rules | Q3 2023-24 | Delayed - External Reasons |  | Whilst the ESO is a co-lead on Primacy we are not wholly responsible for delivery, this is down to industry agreement. We continue to take a proactive role in leading the work, the announcement on Market Facilitator expected in April 24 should provide more clarity on roles and responsibilities giving the ESO more responsibility for delivery and a change to governance
2 | Facilitate distributed flexibility and whole electricity system alignment | D15.8.3 | Enabling whole electricity system operational service co-ordination | Initial operational systems developed for primacy co-ordination based on outputs of requirements and design phase | Q3 2024-25 | On track |  | Project remains on track and confident that it will deliver on time. (these are the solutions for the initial use cases which are being implemented in line with a new two track approach for Primacy)
3 | Net zero operability | D15.9.5 | Provide Early engagement with stakeholders on implementation of technologies required for net zero carbon operation | ESO is supporting stakeholders in implementing new technology developments. Positive feedback from policy makers as applicable | Q4 2024-25 | Continuous activity |  | We continue to develop opportunities for new technologies to provide system and energy services as we progress towards net zero 2035. We are developing new markets and services to meet future system needs, whilst opening these up to new technologies and benefitting the end consumer. We are introducing new ways to manage thermal constraints, meet system stability needs, and gain access to wider reactive power capability. We are seeking new providers of restoration services on distribution networks and delivering a suite of response and reserve products suitable for new technologies.
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.1 | Year ahead regional outage programmes developed in liaison with network parties. | Deliver regional outage programmes | Q4 2023-24 | On track |  | Continuous Activity
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.1 | Year ahead regional outage programmes developed in liaison with network parties. | Deliver regional outage programmes | Q4 2024-25 | On track |  | Continuous Activity
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.2 | Detailed week and day ahead operational documentation produced for National Control | Weekly / Day ahead outage plans | Q4 2023-24 | On track |  | Continuous Activity
3 | Manage access to the system to enable the TOs to undertake work on their assets, liaising with customers where access arrangements impact them | D16.1.2 | Detailed week and day ahead operational documentation produced for National Control | Weekly / Day ahead outage plans | Q4 2024-25 | On track |  | Continuous Activity
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Stakeholder mapping activities commenced | Q1 2023-24 | Complete | Q1 2023-24 | Started Stakeholder mapping exercise
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Stakeholder mapping activities continued and context communicated to stakeholders | Q2 2023-24 | Complete | Q3 2023-24 | Stakeholder mapping exercise completed. Stakeholders invited to OC2 forum in March, where ESO will present initial concept for discussion.
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Organisation of cross industry forum with OC2 attendees to present and hear thoughts | Q3 2023-24 | Complete | Q3 2023-24 | We remain on track for scoping a whole electricity system decision making process. As per the milestone, we delivered an interim OC2 forum in September 2023 and will host a full one in 2024
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | CBA and summary paper written for presentation to industry and ESO senior management | Q4 2023-24 | On track |  | We remain on track for scoping a whole electricity system decision making process.
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Develop framework to facilitate decision making | Q1 2024-25 | On track
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Develop framework to facilitate decision making | Q2 2024-25 | On track |  | Started stakeholder mapping exercise- 1st milestone complete
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Develop framework to facilitate decision making | Q3 2024-25 | On track |  | Started stakeholder mapping exercise- 1st milestone complete
3 | Scope a whole electricity system decision-making policy | D16.2.1 | Great Britain (GB) wide NAP process goes live including extension of the existing SO-TO payment mechanism to the whole of GB. Investigate, with TOs, any further mechanisms that will drive consumer value in this area. Scope the expansion of the process to encompass whole electricity planning and carbon intensity considerations. Implement the processes. | Agree framework to facilitate decision making | Q4 2024-25 | On track |  | Started stakeholder mapping exercise- 1st milestone complete
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.3 | Finalise new processes in readiness for approval of code modifications to facilitate closer working relationships and data exchange/modelling. This will ensure that frameworks support any new enduring processes developed in D16.3.1 and D16.3.2 | Proposals for draft modifications completed | Q4 2023-24 | On track |  | On Track
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.3 | Finalise new processes in readiness for approval of code modifications to facilitate closer working relationships and data exchange/modelling. This will ensure that frameworks support any new enduring processes developed in D16.3.1 and D16.3.2 | Code modifications finalised for approval | Q4 2024-25 | On track |  | On Track
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.4 | Deeper access planning go-live – frameworks, processes and models are in place to facilitate deeper access planning with network parties | Proposals for frameworks, models and processes completed | Q4 2023-24 | On track |  | On track
3 | Work more closely with DNOs and DER to facilitate network access | D16.3.4 | Deeper access planning go-live – frameworks, processes and models are in place to facilitate deeper access planning with network parties | Frameworks, models and processes completed to facilitate deeper access planning. | Q4 2024-25 | On track |  | On track
3 | Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | Dependent on outcomes of A16.3 deliverables | Q3 2023-24 | Delayed - External Reasons |  | Work supported by PODE workstream 1. API links between eNAMS outage management app and NGET's NCIS app commissioned both reading and writing data. Delivers resource planning and efficiency savings for the TO. Working with Scottish Power TO on API proof of concept. Exiting Proof of Concept for Conga, an enhanced reporting tool which may enable users to self serve outage queries and analyse outage planning performance. TOs have been provided with access to an ESO outage tracker, the "ROB" (Regional Outage Board) enabling TOs to track the progress of their outage requests through the ESO outage planning process. Activity completed 16 June 2023
3 | Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | Scoping complete | Q4 2023-24 | On track |  | Work supported by PODE workstream 1
3 | Whole system outage notification | D16.4.1 | Scoping exercise concluded for delivery of enhancements to outage notifications | Dependent on outcomes of A16.3 deliverables | Q4 2024-25 | On track |  | Work supported by PODE workstream 1
3 | Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the ENAMS system (or other) to become a more interactive experience for customers, stakeholders and the market. | Dependent on outcomes of A16.3 deliverables | Q4 2023-24 | On track |  | Work supported by PODE workstream 1
3 | Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the ENAMS system (or other) to become a more interactive experience for customers, stakeholders and the market. | Dependent on outcomes of A16.3 deliverables | Q3 2024-25 | On track |  | Work supported by PODE workstream 1
3 | Whole system outage notification | D16.4.2 | Delivery of enhancements to outage notifications, to stimulate flexibility markets as an additional tool for efficient outage management - we will develop the ENAMS system (or other) to become a more interactive experience for customers, stakeholders and the market. | Whole System Outage Notifications in use | Q4 2024-25 | On track |  | Work supported by PODE workstream 1
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q1 2023-24 | Complete | Q1 2023-24 | The automated stability assessment tool (ASAT) has gone live and we have secured licenses for continuous development and integration (CI/CD). We are working to deliver the same development environment on the cloud.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q2 2023-24 | Complete | Q2 2023-24 | Complete. We will do further enhancements in future and provide with cloud services.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q3 2023-24 | Complete | Q3 2023-24 | SANDBOX environment is up and running and in continuous use.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use and development of sandbox environments | Q4 2023-24 | On track |  | On track for delivery.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q1 2024-25 | On track |  | On track for delivery.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q2 2024-25 | On track |  | On track for delivery.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q3 2024-25 | On track |  | On track for delivery.
3 | Network access planning automation | D16.5.1 | Agreed future platform for any automation and create sandbox environment for application development | Continued use of sandbox environments for A16.5.2 developments | Q4 2024-25 | On track |  | On track for delivery.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Project delivery timelines and full project plan identified for delivery of contingency analysis automation and automation of multiple cardinal point analysis | Q1 2023-24 | Complete | Q1 2023-24
3 | Network access planning automation | D16.5.2 | Scope future automation development | Proof of concept for agreed automation commenced | Q2 2023-24 | Complete | Q2 2023-24 | Work has started and we are on track for delivery.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Proof of concept for automation completed | Q3 2023-24 | Complete | Q3 2023-24 | We have completed the scoping and are preparing for delivery.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training programme for teams in NAP developed and delivery schedule planned | Q4 2023-24 | On track |  | Training has already started with multiple session organized across networks. This will be a continuous activity.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools underway. | Q1 2024-25 | On track |  | Training has already started with multiple session organized across networks. This will be a continuous activity.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools complete and systems in use. | Q2 2024-25 | On track |  | Training has already started with multiple session organized across networks. This will be a continuous activity.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools complete and systems in use. | Q3 2024-25 | On track |  | Training has already started with multiple session organized across networks. This will be a continuous activity.
3 | Network access planning automation | D16.5.2 | Scope future automation development | Training of NAP staff on all tools complete and systems in use. | Q4 2024-25 | On track |  | Training has already started with multiple session organized across networks. This will be a continuous activity.
3 | Network Planning Review | N/A | Network Planning Review | Development of a centralised strategic network planning methodology is complete. | Q4 2024-25 | On track |  | Development of the CSNP, in collaboration with Ofgem and other key stakeholders continued throughout this period, and is continuing at pace. We have responded to the Ofgem CSNP consultations; and Ofgem's decision has been published showing an enhanced role for the FSO.
3 | Offshore Coordination | N/A | Offshore Coordination | ESO activities in the Offshore Transmission Network Review timeline are delivered to the agreed timescales and quality. | Q4 2024-25 | On track |  | On Track based on the plan
2 | Deliver an enhanced platform for EMR | D5.2 | Deliver an enhanced platform for EMR | User familiarisation completed for initial release, with system go live for CM Process. Using portal and data to increase automation of ESO processes to improve efficiency and information available to industry. Guidance to rule changes are incorporated into Portal. The EMR Portal will allow disputes to be linked directly to relevant Applications | Q1 2024-25 | On track |  | All associated milestones are on track, with the CM Go-live planned for May 2024. A user familiarisation phase will be run between mid March to mid April. The Registration window is open for participation. An integrated guidance platform has been designed linked directly with Salesforce to enable guidance to be directly accessed from the new portal. Prioritised improvements have been designed in processes to enable increased automation and enhanced customer journeys.
2 | Deliver an enhanced platform for EMR | D5.2 | Developing the EMR platform | Regulatory changes implemented for annual processes in current EMR Portal. | Q2 2023-24 | Complete | Q2 2023-24 | Changes from the DESNZ consultation were implemented in the portal prior to the Prequalification round opening in July 2023.
2 | Deliver an enhanced platform for EMR | D5.2 | Developing the EMR platform | Regulatory changes implemented for annual processes. | Q2 2024-25 | On track |  | We are working with the DESNZ team to assess and agree changes required on items of work included in the scope of their October consultation. We have designed and developed functionality to implement change to metering processes in accordance with CP373 subject to Ofgem consultation.
2 | Deliver an enhanced platform for EMR | D5.2 | Developing the EMR platform | Deliver planned integration of EMR within the Digital Engagement Platform, considerate of any licensed business separation requirements. Additional improvements to EMR portal to enhance customer experience, following customer feedback. Assessment of delivery options for the Contracts for Difference (CfD) scheme delivery in accordance with REMA proposals. | Q4 2024-25 | On track |  | Initial discussions commenced with the Digital Engagement Platform delivery team. The Delivery Body are designing a feedback methodology that can be used to take customer feedback in line with operational processes run on the New Portal. The Delivery Body continue to monitor REMA proposals to support decisions on future CfD system landscape.