## Log of changes
REF NO. | TITLE AND DESCRIPTION | Proposer | STC/STCP Section to potentially be changed | PROGRESS UPDATE | Next Steps | Date raised as issue to the STC Panel | Date Change Proposal raised to the STC Panel | Route of change | REPORT TO THE AUTHORITY | IMPLEMENTATION [Date of Change]
CM0059 | CM059 Changes to Section C and H following OFGEM Response to Adjudication Request | National Grid | Section C & H and OFTO dispute | Legal text comments to be incorporated and due to be submitted to the September 2017 Panel | To be presented to STC Panel | 2016-09-29 | 2017-09-27 | Self-governance | N/A | TBC
TBC | Section K & EU Network Codes: HVDC (HVDC entered into force Sept 16 and changes to be implemented by Sept 18.) | TBC | Section K | Impacts still be assessed | Impacts still be assessed | Future date | Future date | TBC | TBC | TBC
TBC | SO/TO Funding Mechanism (Section C & D): SO-TO Funding Mechanism: Likely changes as a result of Ofgem driven SO Funding mechanism for BSIS incentive scheme for Scottish TOs, discussed at the joint Ofgem/SO/TO Network Access Policy workgroup | TBC | Section C & D | Impacts still be assessed | Impacts still be assessed | Future date | Future date | TBC | TBC | TBC
TBC | ECIT | TBC | Multiple Sections (Likely to impact Sections B, C, D, E, F, G, H, J, K) | TBC | TBC | Future date | Future date | TBC | TBC | TBC
TBC | Emergency & Restoration (E&R) Network Code: E&R due to enter into force in Q3 2017 | TBC | TBC | Impacts still be assessed | Impacts still be assessed | Future date | Future date | TBC | TBC | TBC
TBC | SO/TO Funding Mechanism (STCP 11-3 & STCP11-4): O-TO Funding Mechanism: Likely changes as a result of Ofgem driven SO Funding mechanism for BSIS incentive scheme for Scottish TOs, discussed at the joint Ofgem/SO/TO Network Access Policy workgroup | TBC |  | 12 month trial ends Mar 2018 and from this will determine if a new STCP (STCP11-4) will be require | Proposer post 12 month trial to send draft proposal to Code Administrator for review before it is taken to Panel. | Future date | Future date | TBC | TBC | TBC
TBC | STCP09-1: Proximity outage | National Grid | STCP09-1 | A final legal review is required to review the changes proposed before a Proposal is submitted to Code Admin for review. Schedule for Oct or Nov 2017 Panel. | TBC | 2016-05-25 | N/A | STCP Change | N/A | TBC
TBC | STCP19-3: Checklist to be reviewed re embedded connections | TBC | STCP19-3 | The marked version has been completed and needs to be shared with TOs for comment. | TBC | Future date | N/A | STCP Change | N/A | TBC

## Changes implemented
REF NO. | TITLE AND DESCRIPTION | Proposer | STC/STCP Section to potentially be changed | PROGRESS UPDATE | Next Steps | Date raised as issue to the STC Panel | Date Change Proposal raised to the STC Panel | Route of change | REPORT TO THE AUTHORITY | IMPLEMENTATION [Date of Change]
PM0097 | STCP18-1: Updating reference to Application Steering Group to Lead Persons | Kenny Stott - SHETL | STCP18-1 | Draft Proposal sent to Code Admin for review | N/A | 2017-06-28 | 2017-06-28 | STCP Change | N/A | 2017-07-25
PM0098 | STCP18-4: Updating reference to Application Steering Group to Lead Persons | Kenny Stott - SHETL | STCP18-4 | Draft Proposal sent to Code Admin for review | N/A | 2017-06-28 | 2017-06-28 | STCP Change | N/A | 2017-07-25
PM0094 | STCP18-2: Updating reference to Application Steering Group to Lead Persons | Kenny Stott - SHETL | STCP18-2 | Implemented 23 May 2017 | N/A | 2017-03-29 | 2017-03-29 | STCP Change | N/A | 2017-05-23
PM0095 | STCP18-3: Updating reference to Application Steering Group to Lead Persons | Kenny Stott - SHETL | STCP18-3 | Implemented 23 May 2017 | N/A | 2017-03-29 | 2017-03-29 | STCP Change | N/A | 2017-05-23
PM0096 | STCP08-02: Missing diagram in Appendix A (last change June 2009) | Caroline Wright Code Administrator | STCP08-2 | Implemented 7 June 2017 | N/A | 2017-05-31 | 2017-05-31 | STCP Change | N/A | 2017-06-07

## changes not being progressed
REF NO. | TITLE AND DESCRIPTION | Proposer | STC/STCP Section to potentially be changed | PROGRESS UPDATE | Next Steps | Date raised as issue to the STC Panel | Date Change Proposal raised to the STC Panel | Route of change | REPORT TO THE AUTHORITY | IMPLEMENTATION [Date of Change]
TBC | Review of Section B Governance: Review Governance arrangements to check fit for purpose and cover STCP approval process | Caroline Wright Code Administrator | Section B | Areas for inclusion being identified for review with National Grid's legal team | Legal confirmed no amendment needed - guidance note to be drafted. | Future date | Future date | TBC | TBC | TBC
TBC | Section K & changes from GC0075: Consequential changes from GC0075 Hybrid Static Compensators | TBC | Section K | TBC | TBC | Future date | Future date | TBC | TBC | TBC
TBC | STCP22-1: Single Scottish model for ETYS production. Being reviewed by the JPC Modelling Subgroup | TBC | STCP22-1 | STCP22-1 is under review by the JPC Modelling Sub Group. | TBC | Future date | N/A | STCP Change | N/A | TBC